## Schedule
Subsys/ Instr | Events | AHEAD Obs. Schedule (DOY) | BEHIND Obs. Schedule (DOY) | Duration (per Obs.) | Real-time Downlink TLM Rate (kbps) (IM/PL/SE/SW/WT/SC) | RTDFD (macro #) | Remarks | Source
All | Note: Schedule set for launch on October 26th (UTC). This results in the A1P maneuver on L+5 days and 9 fewer days between launch and P2.
All | Note: All events are to execute in RT except where noted in the Events column in bold.
All | Note: Telemetry configuration changes are in bold in the Remarks column.
All | Note: Those events shaded light blue are linked together (scheduling relationship) and must be scheduled/moved as a block
All Instru-ments | Note: All instrument events are to be executed serially, first on one S/C, then on the other due to limited instrument support.
All Instru-ments | Note: No instrument SSR data is played back while at 30 kbps downlink rate (L to L + 6 days) due to limited downlink bandwidth.
IMPACT | Enable IMPACT survival power | Prelaunch | Prelaunch | 2 min | 30 | 222 | IMPACT MAG Htr Enabled, Boom Htr & Op Pwr OFF | IMPACT Lead emails 4/29/03, 1/9/04, and 1/20/04
[5 empty] | 0/0/0/0/0/10.1 |  | IMPACT SWEA/STE Surv Pwr ON, Op Pwr OFF
IMPACT SEP/SEPT2 Surv Pwr ON, Op Pwr OFF, Interface Htr (2) OFF
PLASTIC | Enable PLASTIC survival power | Prelaunch | Prelaunch | 2 min | 30 | 222 | PLASTIC Surv Pwr ON, Op Pwr OFF | Obs CDR, 2/21/03
0/0/0/0/0/10.1
SECCHI | Enable SECCHI survival power | Prelaunch | Prelaunch | 2 min | 30 | 222 | SECCHI Surv Pwr ON, Op Pwr OFF, Decontam Htr OFF, Interface Htr OFF | Obs PDR, 12/5/01
0/0/0/0/0/10.1
SWAVES | Disable SWAVES operational power | Prelaunch | Prelaunch | 2 min | 30 | 222 | SWAVES Op Pwr OFF, Replacement Htr ON | Obs PDR, 12/5/01; DAO email 7/8/05
0/0/0/0/0/10.1
| LAUNCH | 1 | 1
***** | AOS First DSN Track - Canberra | BOT + 6 min | BOT + 6 min
RF | Event #1 – Establish command uplink | BOT + 30 min | BOT + 35 min | 5 min | 30 | 222 | Sweep BLT +10 KHz to -10 KHz & hold at 320 Hz/sec | RF Lead memo, SER-06-039, 5/15/06
[5 empty] | 0/0/0/0/0/10.1 |  | Activate 2 kbps uplink at 200 W for -65 dBm at S/C
Doppler -140 KHz
PWR | Event #2 - Enable PPT | BOT + 35 min | BOT + 40 min | 5 min | 30 | 222 | Disabled at launch | Launch Proc mtg, 6/21/05
[5 empty] | 0/0/0/0/0/10.1 |  | Script: ppt_enable.prc
C&DH | Event #3 – Start Playback SSR | BOT + 40 min | BOT + 45 min | 5 min | 30 | 222 | Routine partitions & G&C blackbox set to block for launch (G&C Routine overwrites at 1.5 hrs from last playback) Macro 421. Reinforce macro 222 to set PB ratio to 2 since autonomy rule 190 will set it to 0. | Mission Sim #1 dev, 1/15/05
[5 empty] | 0/0/0/0/0/10.1 |  | Script: ssr_pb_begin.prc
S/C | Event #4 -Verify post launch S/C configuration | BOT + 45 min | BOT + 50 min | 10 min | 30 | 222 | Script: launch_first_contact_ck.prc | Mission Sim #1B, 4/22/05
0/0/0/0/0/10.1
C&DH | Event #5 - Change to first week TLM generation/record/RT downlink for S/C HSKP | BOT + 55 min | BOT + 60 min | 5 min | 30 | 231 | 9.5 kbps, Adds G&C Standby mode pkt @ 4/min and removes G&C Ascent and Maneuver mode pkts, macro 231, PB ratio 2, Starts SSR playback with single command | Mission Sim #1B, 4/22/05
[5 empty] | 0/0/0/0/0/9.5 |  | Script: first_week_tlm_setup.prc
THRM | Event #6 - Reinforce Enabling of all S/C Heaters | BOT + 60 min | BOT + 65 min | 5 min | 30 | 231 | Need OK from Pwr Lead before enabling. LPS (6), Battery (2), HGA (2), & S/C Surv (5) | Autonomy Rule Rev., 8/27/03
[5 empty] | 0/0/0/0/0/9.5 |  | Script: htr_config.prc
G&C/EA | Event #7 - Load all flight G&C and EA parameters to EEPROM and RAM from object release | BOT + 65 min | BOT + 70 min | 30 min | 30 | 231 | Loads HGA caged parameter to caged. | Fault Prot. Req. Doc. Rev, 5/20/02
[5 empty] | 0/0/0/0/0/9.5 |  | ce_ea_param_mom_redlimit = 14
ce_ea_param_mom_whitelimit = 20
ce_ea_param_thr_taudz = 5
ce_ea_param_ena_actuators_delay 0
gc_param_mom_momfilton = 1
gc_param_ads_filttype = 0
gc_param_mom_redlimit = 20
gc_param_mom_momgain = 0.0085
gc_param_mom_whitelimit = 25
gc_param_thr_ratemax = 0.002
gc_param_aut_mom_dmp = 1, 4, 420, 25, SET_A, SET_B
gc_param_mom_momintgain = 0.000038
PWR | Event #8 – Change PDU Separation Status TLM Words to Command Status TLM Words | BOT + 95 min | BOT + 100 min | 5 min | 30 | 231 | Launch with separation status TLM words. CCD only cmds: | FP mtg, 11/15/05
[5 empty] | 0/0/0/0/0/9.5 |  | CCD_CD_TO_CMD_STATUS_A CCD_CD_TO_CMD_STATUS_B
Script: PDU_status_words_command.prc
PWR | Event #9 – Change HLVS settings for flight | BOT + 100 min | BOT + 105 min | 5 min | 30 | 231 | Launch with lowest pressure settings and 25.5 V & LVSSA Off | FP email, 1/19/06
[5 empty] | 0/0/0/0/0/9.5 |  | For flight, LVSSA & B On, 26.5 V,
LVSSA = AHEAD = 500 psi, BEHIND = 454 psi LVSSB = AHEAD = 504 psi, BEHIND = 522 psi
Script: hlvs_enable.prc
C&DH/EA | Event #10 – Clear prelaunch macro and relative timetag bins 480 in RAM & EEPROM | BOT + 105 min | BOT + 110 min | 5 min | 30 | 231 | Used to enforce catbed A primary heaters on, XPNDR exciter on, and BLF timeout enabled. | Launch Sim, 5/15/06
[5 empty] | 0/0/0/0/0/9.5 |  | Script: clear_macro_480.prc
ME | Event #11 - HGA Deployment | BOT + 130 min | BOT + 135 min | 15 min | 30 | 232 | Telltale at full deployment | RF Lead
[5 empty] | 3.2/1/1.8/2.2/0/26.1 |  | Stops SSR playback w/ single cmd
switch S/C HSKP to maneuver to record high rate IMU data, macro 232, PB ratio zero, then Selects RTDFD 14 to downlink G&C blackbox data in RT (26.1 kbps total). After deployment has been verified, switch RFDFD to macro 231, PB ratio 2, Starts SSR playback with single command
Script: hga_deploy.prc
ME | Event #12 - HGARA power on | BOT + 145 min | BOT + 150 min | 5 min | 30 | 231 | After HGA deployment has been confirmed. Reset HGA Control in G&C before powering | ME Lead phone call, 3/14/03
[5 empty] | 0/0/0/0/0/9.5 |  | Script: hgara_pwr_on.prc
G&C | Event #13 - Load new HGA pointing parameter before pointing | BOT + 150 min | BOT + 155 min | 5 min | 30 | 231 | Launch default is stowed (caged) position. After HGA deployment change to uncaged. Execute after loading G&C flight parameters event. RAM only. | Fault Prot. Req. Doc. Rev, 5/20/02
[5 empty] | 0/0/0/0/0/9.5 |  | Script: hga_point_parm_uncaged.prc
SECCHI | Event #14 - Power-up decontamination heaters using duty cycle macro and reinforce launch configuration of all instrument survival powers and heaters | BOT + 155 min | BOT + 160 min | 5 min | 30 | 231 | Need OK from Pwr Lead before turning on. SECCHI Decon. Heaters must be ON no earlier than 90 minutes after S/C separation and no later than EOT. Use duty cycle 65 seconds on and 55 seconds off in macro 492. | Obs PDR, 12/5/01. DAO email 7/8/05
[5 empty] | 0/0/0/0/0/9.5 |  | Leave on for 30 days, OFF for maneuvers.
[7 empty] | IMPACT MAG Htr Enabled, Boom Htr & Op Pwr OFF | System Lead email, 2/10/06
IMPACT SWEA/STE Surv Pwr ON, Op Pwr OFF
[7 empty] | IMPACT SEP/SEPT2 Surv Pwr ON, Op Pwr OFF, Interface Htr (2) OFF | SECCHI Lead email, 6/28/06
PLASTIC Surv Pwr ON, Op Pwr OFF
SECCHI Surv Pwr ON, Op Pwr OFF, Decontam Htr ON, Interface Htr OFF
SWAVES Op Pwr OFF, Replacement Htr ON
Script: decon_on_inst_config.prc
C&DH | Event #15 - Stop SSR playback and Set G&C and C&DH Routine partitions to overwrite | EOT - 5 min | EOT - 5 min | 2 min | 30 | 231 | Stop SSR playback, macro 449, C&DH & G&C Routine partitions & G&C blackbox set to overwrite | Mission Sim #1 dev, 1/15/05
[5 empty] | 0/0/0/0/0/9.5 |  | Script: ssr_pb_stop.prc
***** | AOS 2nd DSN Track - Madrid
C&DH | Event #16 - Start SSR Playback, S/C data only | 1 | 1 | 2 min | 30 | 231 | Macro 421
0/0/0/0/0/9.5
RF | Event #17 - Enable Transponder Ranging | 1 | 1 | 2 min | 30 | 231 | No attenuator on 2nd track. | RF Lead Email 6/27/03
[5 empty] | 0/0/0/0/0/9.5 |  | Modulation index = 0.611 rad
Set after BOT of second track
DSS to use MAQ sweep template
Script: xpnder_ranging_enable.prc
C&DH | Event #18 - Increase Visible Couter Packets Frequency | 1 | 1 | 2 min | 30 | 231 | APIDs 017, 018, & 019 to 1/min. Macro 449 will set back to 1/12 hours | Fault Prot, 10/16/06
[5 empty] | 0/0/0/0/0/9.5 |  | Script: vis_ctr_tlm_on.prc
C&DH | Event #19 - Clear Autonomy Counters | 1 | 1 | 2 min | 30 | 231 | This should be done before loading Flight Autonomy. Clears all counters, autonomy history buffers, and firing telltales. | Fault Prot, 10/16/06
[5 empty] | 0/0/0/0/0/9.5 |  | Script: autonomy_prelaunch_clear_status.prc
C&DH/EA | Event #20 - Load flight autonomy rules and macros | 1 | 1 | 2 hrs | 30 | 231 | Refer to FP Spec, section 4.1.2.2 Load to EEPROM1, 2, & RAM. Load script options: EE2, No, EE1, Yes, select copy 1 after loading. | Fault Prot. Peer Rev, 12/10/02
[5 empty] | 0/0/0/0/0/9.5 |  | Script: load_autonomy_launch_to_flight.prc
C&DH | Event #21 - Disable Rule 25 (Monitor HGA health when HGA is operated) | 1 | 1 | 2 min | 30 | 231 | This should be done after loading Flight Autonomy. | Fault Prot. mtg, 10/6/06
[5 empty] | 0/0/0/0/0/9.5 |  | Script: disable_rule_25.prc
C&DH | Event #22 - Change SCLT delay to 24 hrs in C&DH and EA | 1 | 1 | 2 min | 30 | 231 | Launch SCLT = 8 hrs. Update storage variables 0 & 1 to 24 hrs. Disable 191 & 192 autonomy rules before modifying storage variables. Also clears rules 189 & 190 fire counts. | Fault Prot. Peer Rev, 12/10/02
[5 empty] | 0/0/0/0/0/9.5 |  | Script: sclt_24hrs.prc
***** | AOS 3rd DSN Track - Goldstone
RF | Switch to –Z LGA | 1 | 1 | 5 min | 30 | 244 | Schedule to switch at the end of the track before handing over to the next DSS since antenna polarity is changing from LCP to RCP. | RF phone call, 3/14/03
3.2/1/1.8/2.2/0/3.3
***** | AOS DSN Track - Canberra
***** | Mission Day 2
RF | Step HGARA | 2 | 2 | 5 min | 30 | 231 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 0/0/0/0/0/9.5 |  | Script: hgara_step.prc
***** | AOS DSN Track - Madrid
C&DH | Stop SSR Playback | 2 | 2 | 2 min | 30 | 231 | SECCHI pwr on uses too much RT downlink and SSR PB not possible when RT TLM > 15 kbps @ 30 kbps downlink rate. Stops SSR playback w/ single cmd | Mission Sim #2, 10/12/05
[5 empty] | 0/0/0/0/0/9.5 |  | Script: ssr_playback_disable.prc
C&DH | Change to RTDFD 243 - 30 kbps - Day 2, SECCHI Power On 0/0/19/0/0/9.5, Phasing Orbit | 2 | 2 | 2 min | 30 | 243 | Enable 19 kbps RT TLM for SECCHI, macro 243, PB ratio zero | Early Ops Rev, 5/31/06
0/0/19/0/0/9.5
SECCHI | Switch ON SECCHI Operational Power | 2 | 2 | 5 min | 30 | 243 | SECCHI Surv Pwr OFF, Op Pwr ON, Decontam Htr ON, Interface Htr OFF | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04.
[5 empty] | 0/0/19/0/0/9.5 |  | Macro 498
SECCHI | Perform SECCHI Electronics/software Abbrev. Funct Test | 2 | 2 | 2 hrs | 30 | 243 | Serially on STA and STB | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04.
[5 empty] | 0/0/19/0/0/9.5 |  | Exclusive commanding required
SECCHI | Move EUVI, COR1, & COR2 doors from Superclosed to Closed. | 2 | 2 | 20 min | 30 | 243 | Serially on STA and STB | SECCHI Telecon 1/23/04. COR1/2 door openings: M-O-R 11/04.
[5 empty] | 0/0/19/0/0/9.5 |  | Exclusive commanding required
***** | AOS DSN Track - Goldstone
C&DH | Change to RTDFD 232 - 30 kbps - Delta V maneuvers, S/C & Instruments, 3.2/1/1.8/2.2/0/8.4 | 2 | 2 | 2 min | 30 | 232 | Enable all instrument RT TLM, switch S/C HSKP to maneuver to record high rate IMU data, no space weather allocation due to bandwidth limitations, macro 232, Set PB ratio to 1 | Early Ops Rev, 5/31/06
[5 empty] | 3.2/1/1.8/2.2/0/9.4 |  | Script: rtdfd12_pb1.prc
C&DH | Start SSR Playback | 2 | 2 | 2 min | 30 | 232 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/1/1.8/2.2/0/9.4 |  | Script: ssr_playback_enable.prc
SWAVES | Power-up aliveness check | 2 | 2 | 2 hrs | 30 | 232 | Serially on STA and STB | SWAVES CDR, 2/12/03; SWAVES email 12/17/03; DAO email 7/8/05
[5 empty] | 3.2/1/1.8/2.2/0/9.4 |  | SWAVES Op Pwr ON, Replacement Htr OFF
Macro 499
SWAVES | Deploy SWAVES antennas | 2 | 2 | 1 hr | 30 | 232 | Serially on STA and STB | SWAVES CDR, 2/12/03; SWAVES email 12/17/03;
[5 empty] | 3.2/1/1.8/2.2/0/9.4 |  | Dependent on G&C maneuvering recommendation Need RT cmd & TLM, deploy 1 antenna, observe 20 minutes, repeat for other 2 antennas | SWAVES presentation for MOR 11/09/04
Script: swaves_antenna_deploy.prc
G&C | Load new G&C mass properties after SWAVES Antenna deployments | 2 | 2 | 2 min | 30 | 232 | One each may be required for HGA deployment, SWAVES, and IMPACT boom | G&C Lead, 5/22/02; SWAVES email 12/17/03
[5 empty] | 3.2/1/1.8/2.2/0/9.4 |  | Script:
C&DH | Change to RTDFD 244 - 30 kbps - Days 2 to 6, 3.2/1/1.8/2.2/0/3.3, Phasing Orbit | 2 | 2 | 2 min | 30 | 244 | Enable all instrument RT TLM, switch S/C HSKP to nominal, no space weather allocation due to bandwidth limitations, macro 244, Set PB ratio 2 | Early Ops Rev, 5/31/06
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | Script: rtdfd24_pb2.prc
***** | Mission Day 3
ME | Close umbilical cover | 3 | 3 | 2 min | 30 | 244 | After SWAVES deployment so SWAVES can characterize noise level with it open | SWAVES email, 5/19/06
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | Script: close_umbilical_cover.prc
IMPACT | Power-up IDPU. IDPU/MAG preliminary checkout | 3 | 3 | 30 min. | 30 | 244 | Serially on STA and STB | IMPACT Lead email 4/29/03. TLM and SSR usage per lead worksheet 2-17-2004. STE removed per M-O-R 11/04.
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | IMPACT MAG Htr Enabled, Boom Htr Disabled & Op Pwr ON
Macro 494
IMPACT | Power-up SWEA. SWEA preliminary checkout | 3 | 3 | 30 min | 30 | 244 | IMPACT SWEA/STE Surv Pwr OFF, Op Pwr ON | IMPACT Lead email 4/29/03. TLM and SSR usage per lead worksheet 2-17-2004. STE removed per M-O-R 11/04.
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | Macro 495
IMPACT | Deploy SWEA cover | 3 | 3 | 2 min | 30 | 244 | After IDPU power-up. Non-reclosable cover. Deployment cmd and verification controlled by POC | IMPACT Lead email 4/29/03; autonomy rule note – DAO email 12/31/03. TLM and SSR usage per lead worksheet 2-17-2004. Impact Lead email 8/15/05
3.2/1/1.8/2.2/0/3.3
IMPACT | Complete IDPU/MAG/SWEA checkout | 3 | 3 | 2-4 hrs | 30 | 244 |  | IMPACT Lead email 4/29/03. TLM and SSR usage per lead worksheet 2-17-2004. STE moved to Day 19 per M-O-R 11/04
3.2/1/1.8/2.2/0/3.3
C&DH | Change to RTDFD 232 - 30 kbps - Delta V maneuvers, S/C & Instruments, 3.2/1/1.8/2.2/0/8.4 | 3 | 3 | 2 min | 30 | 232 | Enable all instrument RT TLM, switch S/C HSKP to maneuver to record high rate IMU data, no space weather allocation due to bandwidth limitations, macro 232, Set PB ratio to 1 | Early Ops Rev, 5/31/06
[5 empty] | 3.2/1/1.8/2.2/0/9.4 |  | Script: rtdfd12_pb1.prc
G&C/LPS | Conduct 1st Engineering Burn as an end-to-end test of G&C and LPS | 3 | 3 | 3 hrs | 30 | 232 | Before A1 burn. G&C to use default PDU side B. Need same S/C deployment config. as will be used in A1 burn. | Maneuver CONOPs mtg, 6/3/02
3.2/1/1.8/2.2/0/9.4
C&DH | Change to RTDFD 244 - 30 kbps - Days 2 to 6, 3.2/1/1.8/2.2/0/3.3, Phasing Orbit | 3 | 3 | 2 min | 30 | 244 | Enable all instrument RT TLM, switch S/C HSKP to nominal, no space weather allocation due to bandwidth limitations, macro 244, Set PB ratio 1 | Early Ops Rev, 5/31/06
3.2/1/1.8/2.2/0/3.3
C&DH | Start SSR Playback | 3 | 3 | 2 min | 30 | 244 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | Script: ssr_playback_enable.prc
PLASTIC | Power-up and functional test | 3 | 3 | 2 hrs | 30 | 244 | Low voltages only. PLASTIC Surv Pwr OFF, Op Pwr ON | PLASTIC PDR, 9/25/02. OWGM 4/21/04
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | Macro 497
***** | Mission Day 4
C&DH | Update PBDFDs in C&DH EEPROM & RAM | 4 | 4 | 2 min | 30 | 244 | Seven Instrument PBDFD (6, 8, 10, 12, 15, 18, & 21 corresponding to 10, 30, 96, 160, 360, 480, & 720 kbps) are incorrectly set. The two SECCHI science partition playback allocations are misproportioned at 99 to 1%. Should be 95% synoptic to 5% special event. | CR 5143 Systems email, 7/26/06
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | Script: ahead_load_SECCHI_pbdfds.prc
PWR | Solar Array Production Test | 4 | 4 | 1 hr | 30 | 244 | Cannot determine SA production w/ PPT ON. Disable PPT, high charge rate, and high VT level. | PWR Lead Email 8/19/04
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | Script:
IMPACT | SWEA HVPS power-up and test | 4 | 4 | 1-2 hrs | 30 | 244 | No earlier than 24 hrs after SWEA cover deployment. | IMPACT Lead email 4/29/03
3.2/1/1.8/2.2/0/3.3
S/C | Test timekeeping system and updating | 4 | 4 | 2 min | 30 | 244 | Before A1 burn | SEPR RFA #2, 4/16/02
3.2/1/1.8/2.2/0/3.3
***** | Mission Day 5
***** | AOS Next DSN Track - Pre-Maneuver
C&DH | Abort SECCHI Decontamination Heater Duty Cycling Macro | 303 | 303 | 2 min | 30 | 244 | Abort relative TT #6 and #7 | System Lead email, 2/10/06
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | SECCHI Decon. Heater Pwr OFF
6 hrs before delta V maneuver
Script: secchi_decon_heater_stick_off.prc
***** | AOS DSN Track – Maneuver
C&DH | Change to RTDFD 232 - 30 kbps - Delta V maneuvers, S/C & Instruments, 3.2/1/1.8/2.2/0/8.4 | 303 | 303 | 2 min | 30 | 232 | Enable all instrument RT TLM, switch S/C HSKP to maneuver to record high rate IMU data, no space weather allocation due to bandwidth limitations, macro 232, Set PB ratio to 1 | Early Ops Rev, 5/31/06
[5 empty] | 3.2/1/1.8/2.2/0/9.4 |  | Script: rtdfd12_pb1.prc
S/C | A1 Prime Delta V Maneuver | 303 | 303 | 4 hrs | 30 | 232 | Deterministic. Not needed for a nominal orbit insertion for launch on Day 1 or 2 | Mission Design, 7/11/2005
3.2/1/1.8/2.2/0/9.4
C&DH | Change to RTDFD 244 - 30 kbps - Days 2 to 6, 3.2/1/1.8/2.2/0/3.3, Phasing Orbit | 303 | 303 | 2 min | 30 | 244 | Enable all instrument RT TLM, switch S/C HSKP to nominal, no space weather allocation due to bandwidth limitations, macro 244, Set PB ratio 1 | Early Ops Rev, 5/31/06
3.2/1/1.8/2.2/0/3.3
C&DH | Start SSR Playback | 303 | 303 | 2 min | 30 | 244 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | Script: ssr_playback_enable.prc
***** | AOS DSN Track – Post Maneuver
SECCHI | Enable MOps SECCHI Decontamination Heater Duty Cycling Macro | 303 | 303 | 2 min | 30 | 244 | Use duty cycle 65 seconds on and 55 seconds off in macro 492 & 493 | Systems Eng, 5/26/06
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | 6 hrs after delta V maneuver
Script: secchi_decon_htr_on.prc
***** | Mission Day 6
RF | Step HGARA | 304 | 304 | 5 min | 30 | 244 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/1/1.8/2.2/0/3.3 |  | Script: hgara_step.prc
S/C | A1 Backup #1 Delta V Maneuver | 304 | 304 | 4 hrs | 96 | 234 | Deterministic. Not needed for a nominal orbit insertion for launch on Day 1 or 2. Only if prime maneuver was not successful. | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
***** | Mission Day 7
RF | Switch to 360 kbps downlink rate | 305 | 305 | 2 min | 360 | 237 | On start of Day 7 | RF Lead email, 4/16/03
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Macro 213, biphase-L
S/C | A1 Backup #2 Delta V Maneuver | 305 | 305 | 4 hrs | 96 | 234 | Deterministic. Not needed for a nominal orbit insertion for launch on Day 1 or 2. Only if prime & backup #1 maneuvers were not successful. | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
IMPACT | Power-up Boom Deployment Heater and Deploy IMPACT SW/MAG boom | 305 | 305 | 1-2 hrs | 360 | 234 | Boom deployment heater needs to be on 30 min (and in sunlight) before boom deployment. After that, it never needs to be on. Ensure that rule 97 (IMPACT Boom High Temp) is enabled. No boom deployment telltale – use RT MAG data. Macro 234. Downlink in RT G&C maneuver TLM. Set PB ratio to 8. After deployment, switch RTDFD to macro 237 | PDR, 9/11/01
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Script: impact_boom_deploy.prc | IMPACT Lead email 4/29/03. TLM and SSR usage per lead worksheet 2-17-2004
G&C | Load new G&C mass properties after IMPACT Boom deployment | 305 | 305 | 2 min | 360 | 237 | One each may be required for HGA deployment, SWAVES, and IMPACT boom | G&C Lead, 5/22/02
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script:
***** | Switch from continuous DSN coverage to 3 hour tracks centered every 24 hours | 306 | 306
C&DH/EA | Disable launch SCLT autonomy rules | 306 | 306 | 2 min | 360 | 237 | On Day 8 since DSN tracks now 3 hrs each day | Fault Prot. Peer Rev, 12/10/02
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Update storage variables 0 & 1 to 80 hrs (never be reached). Disable 191 & 192 autonomy rules before modifying storage variables.
Script: sclt_80hrs.prc
C&DH | Change to RTDFD 234 - 96 kbps - Delta V maneuvers, S/C & Instruments | 306 | 306 | 2 min | 96 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/26.1
G&C | Switch G&C to use PDU side A | 306 | 306 | 2 min | 96 | 234 | Test redundant thruster electrical path | EACDRPR-10 AI response, 5/5/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Script: switch_to_pdu_side_a.prc
G&C/LPS | Conduct 2nd Engineering Burn to test A side thruster electrical path | 306 | 306 | 3 hrs | 96 | 234 | P1 – 3 days and after IMPACT boom deployment | EACDRPR-10 AI response, 5/5/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Switch G&C to use PDU side A. Same as Engineering Burn on day 3.
G&C | Switch G&C to use PDU side B (default) | 306 | 306 | 2 min | 96 | 234 | Switch thruster electrical path to default side | EACDRPR-10 AI response, 5/5/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Script: switch_to_pdu_side_b.prc
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 306 | 306 | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Start SSR Playback | 306 | 306 | 2 min | 360 | 237 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ssr_playback_enable.prc
RF | HGA Stepped Slew Test | 307 | 307 | 30 min | 360 | 237 | Disable autonomy rule 25 (Monitor HGA health) before each test. | Systems Eng, 10/10/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: shga_slew_to_x.prc
RF | Step HGARA | 308 | 308 | 5 min | 360 | 237 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
PLASTIC | Internal Pulser Test | 308 | 308 | 3 hrs | 360 | 237 | First hour for set-up, last 1/2 hour for contingency action. Central part for observation | PLASTIC-Ops WGM 4/21/04. PLASTIC lead email 9/1/05
3.2/3.2/3.6/2.2/0.6/3.3
PLASTIC | SSD to Op levels. | 309 | 309 | 3 hrs | 360 | 237 | First hour for set-up, last 1/2 hour for contingency action. Central part for observation | PLASTIC-Ops WGM 4/21/04. PLASTIC M-O-R presentation 11/10/04. PLASTIC lead email 9/1/05
3.2/3.2/3.6/2.2/0.6/3.3
***** | AOS Next DSN Track - Pre-Maneuver
SECCHI | Close COR1, COR2, & EUVI doors | 310 | 310 | 20 min | 360 | 237 | SECCHI reclosable doors are not grounded and could arc while passing through the radiation belts. | System Eng Lead email, 5/15/03
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Switch OFF SECCHI Operational Power | 310 | 310 | 5 min | 360 | 237 | SECCHI Surv Pwr ON, Op Pwr OFF, Interface Htr Off | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04.
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Decontamination Power to remain ON.
C&DH | Abort SECCHI Decontamination Heater Duty Cycling Macro | 310 | 310 | 2 min | 360 | 237 | Abort relative TT #6 and #7 | System Lead email, 2/10/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | SECCHI Decon. Heater Pwr OFF
6 hrs before delta V maneuver
Script: secchi_decon_heater_stick_off.prc
SWAVES PLASTIC | Power down before P1 Maneuver | 310 | 310 | 10 min | 360 | 237 | If needed. Baseline instru. off during maneuvers due to power limitations. PLASTIC OFF prior to IMPACT IDPU OFF. SWAVES off last. IMPACT MAG Htr Enabled, Boom Htr & Op Pwr OFF | SRD. PLASTIC-Ops WGM 4/21/04. . SWAVES - MOR D-R #2 10/28/04. DAO email 7/8/05
IMPACT |  |  |  | 1 hr PLASTIC | 3.2/3.2/3.6/2.2/0.6/3.3 |  | IMPACT SWEA/STE Surv Pwr ON, Op Pwr OFF
IMPACT SEP/SEPT2 Surv Pwr ON, Op Pwr OFF, Interface Htr (2) OFF
PLASTIC Surv Pwr ON, Op Pwr OFF
SWAVES Op Pwr OFF, Replacement Htr ON
***** | AOS DSN Track – Maneuver
C&DH | Change to RTDFD 234 - 96 kbps - Delta V maneuvers, S/C & Instruments | 310 | 310 | 2 min | 96 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/26.1
S/C | P1 Delta V Maneuver | 310 | 310 | 4 hrs | 96 | 234 | Non-deterministic. | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 310 | 310 | 2 min | 360 | 237 | Macro 213. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Start SSR Playback | 310 | 310 | 2 min | 360 | 237 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ssr_playback_enable.prc
S/C | Ranging capability test of the DSS with Attenuator installed | 310 | 310 | 2 min | 96 | 234 | P1 track | FDF Lead email, 5/19/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Configure XPNDR & DSS for ranging with attenuator in at DSS
S/C | Test system reset and EA mode - AHEAD only | 310 | -- | 6 hrs | 96 | 290 | Schedule after S/C has recovered from P1 burn and when SPE angle is favorable. May need additional track time. Schedule when system momentum is low. | SEPR RFA, 11/02
[5 empty] | 0/0/0/0/0/3.1 |  | Will power off all instruments and ST
Ensure UTCF and S/C ephemeris in EE is the latest. S/C rolls clockwise when viewed along +X (looking at the Sun). Will lose all stored timetag commands. Plan to reload UT events after recovery.
Script:
***** | AOS DSN Track – Post Maneuver
SWAVES IMPACT | Power and recover SWAVES and IMPACT from P1 Maneuver & EA mode test. PLASTIC turn on SSDs again, Pac to 5kV then 10kV | 310 | 310 | 1 hr | 360 | 237 | SWAVES power-up first. IDPU & SWEA/STE-D only for IMPACT. PLASTIC ON after IMPACT IDPU | SRD. PLASTIC-Ops WGM 4/21/04. . SWAVES - MOR D-R #2 10/28/04. PLASTIC M-O-R presentation 11/10/04. DAO email 7/8/05. IMPACT Lead email 8/15/05
PLASTIC |  |  |  | 3 hrs PLASTIC | 3.2/3.2/3.6/2.2/0.6/3.3 |  | IMPACT MAG Htr Enabled, Boom Htr OFF, & IDPU Op Pwr ON
IMPACT SWEA/STE Surv Pwr OFF, Op Pwr ON
PLASTIC Surv Pwr ON, Op Pwr ON
SWAVES Op Pwr ON, Replacement Htr OFF. IMPACT ramp up SWEA HV (5 minutes)
SECCHI | Enable MOps SECCHI Decontamination Heater Duty Cycling Macro | 310 | 310 | 2 min | 360 | 237 | Use duty cycle 65 seconds on and 55 seconds off in macro 492 & 493 | Systems Eng, 5/26/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | 6 hrs after delta V maneuver
Script: secchi_decon_htr_on.prc
SECCHI | Power ON SECCHI Operational Power | 310 | 310 | 20 min | 360 | 237 | SECCHI Surv Pwr OFF, Op Pwr ON, Decontam Htr ON, Interface Htr OFF | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04.
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | 310 | -- | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI | Perform Functional Test – AHEAD only (1 of 3) | 310 | -- | 3 hrs | 360 | 245 |  | Early Ops Rev, 5/31/06
3.2/3.2/93/2/0/3.3
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 310 | -- | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Crack open EUVI, COR1, & COR2 doors. | 311 | 311 | 20 min | 360 | 237 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06 SECCHI Ops Lead email, 10/4/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | 311 | -- | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI | Perform SECCHI Electronics/Software Functional Test – AHEAD only (2 of 3) | 311 | -- | 3 hrs | 360 | 245 | 20 min/mech (6) = 2 hrs | SECCHI CDR, 11/6/02. SECCHI M-O-R presentation 11/10/04.
[5 empty] | 3.2/3.2/93/2/0/3.3 |  | 30 min/CEB (2) = 1 hr
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 311 | -- | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
RF | Step HGARA | 312 | 312 | 5 min | 360 | 237 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | 312 | -- | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI | Perform Functional Test of SECCHI Mechanisms and Cameras – AHEAD only (3 of 3) | 312 | -- | 3 hrs | 360 | 245
3.2/3.2/93/2/0/3.3
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 312 | -- | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | -- | 313 | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI | Perform Functional Test – BEHIND only (1 of 3) | -- | 313 | 3 hrs | 360 | 245 |  | Early Ops Rev, 5/31/06
3.2/3.2/93/2/0/3.3
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | -- | 313 | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | -- | 314 | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI | Perform SECCHI Electronics/Software Functional Test – BEHIND only (2 of 3) | -- | 314 | 3 hrs | 360 | 245 | 20 min/mech (6) = 2 hrs | SECCHI CDR, 11/6/02. SECCHI M-O-R presentation 11/10/04.
[5 empty] | 3.2/3.2/93/2/0/3.3 |  | 30 min/CEB (2) = 1 hr
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | -- | 314 | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | -- | 315 | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI | Perform Functional Test of SECCHI Mechanisms and Cameras – BEHIND only (3 of 3) | -- | 315 | 3 hrs | 360 | 245
3.2/3.2/93/2/0/3.3
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | -- | 315 | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
***** | AOS DSN Track – Pre-Maneuver
SECCHI | Close COR1, COR2, & EUVI doors | 315 | 315 | 20 min | 360 | 237 |  | System Eng Lead email, 5/15/03
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Switch OFF SECCHI Operational Power | 315 | 315 | 5 min | 360 | 237 | SECCHI Surv Pwr ON, Op Pwr OFF, Interface Htr Off | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04.
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Decontamination Power to remain ON.
C&DH | Abort SECCHI Decontamination Heater Duty Cycling Macro | 315 | 315 | 2 min | 360 | 237 | Abort relative TT #6 and #7 | System Lead email, 2/10/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | SECCHI Decon. Heater Pwr OFF
6 hrs before delta V maneuver
Script: secchi_decon_heater_stick_off.prc
SWAVES PLASTIC IMPACT | Power down before A2 Maneuver | 315 | 315 | 10 min | 360 | 237 | If needed. Baseline instru. off during maneuvers due to power limitations. PLASTIC OFF prior to IMPACT IDPU OFF. SWAVES off last. IMPACT MAG Htr Enabled, Boom Htr & Op Pwr OFF | SRD. PLASTIC-Ops WGM 4/21/04. . SWAVES - MOR D-R #2 10/28/04. DAO email 7/8/05
|  |  |  | 30 min PLASTIC | 3.2/3.2/3.6/2.2/0.6/3.3 |  | IMPACT SWEA/STE Surv Pwr ON, Op Pwr OFF
IMPACT SEP/SEPT2 Surv Pwr ON, Op Pwr OFF, Interface Htr (2) OFF
PLASTIC Surv Pwr ON, Op Pwr OFF
SECCHI Surv Pwr ON, Op Pwr OFF, Interface Htr Off, SWAVES Op Pwr OFF, Replacement Htr ON.
***** | AOS DSN Track – Maneuver
C&DH | Change to RTDFD 234 - 96 kbps - Delta V maneuvers, S/C & Instruments | 315 | 315 | 2 min | 96 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/26.1
S/C | A2 Prime Delta V Maneuver | 315 | 315 | 4 hrs | 96 | 234 | Non-deterministic | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 315 | 315 | 2 min | 360 | 237 | Macro 213. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Start SSR Playback | 315 | 315 | 2 min | 360 | 237 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ssr_playback_enable.prc
***** | AOS DSN Track – Post Maneuver
| Power and recover SWAVES, IMPACT, and PLASTIC from A2 Maneuver | 315 | 315 | 1 hr | 360 | 237 | If needed. SWAVES power-up first. IDPU, SWEA/STE-D, & SEP for IMPACT. PLASTIC ON after IMPACT IDPU | SRD. PLASTIC-Ops WGM 4/21/04. . SWAVES - MOR D-R #2 10/28/04. DAO email 7/8/05/ IMPACT Lead email 8/15/05.
SWAVES PLASTIC IMPACT |  |  |  | two 1-hr obs PLASTIC | 3.2/3.2/3.6/2.2/0.6/3.3 |  | IMPACT MAG Htr Enabled, Boom Htr OFF, & IDPU Op Pwr ON
IMPACT SWEA/STE Surv Pwr OFF, Op Pwr ON
IMPACT SEP/SEPT2 Surv Pwr OFF, Op Pwr ON, Interface Htr (2) OFF
PLASTIC Surv Pwr ON, Op Pwr ON
SWAVES Op Pwr ON, Replacement Htr OFF.
IMPACT: ramp up SWEA HV, configure SEP, and ramp up SIT HVPS (~15 minutes.)
SECCHI | Enable MOps SECCHI Decontamination Heater Duty Cycling Macro | 315 | 315 | 2 min | 360 | 237 | Use duty cycle 65 seconds on and 55 seconds off in macro 492 & 493 | Systems Eng, 5/26/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | 6 hrs after delta V maneuver
Script: secchi_decon_htr_on.prc
SECCHI | Power ON SECCHI Operational Power | 315 | 315 | 20 min | 360 | 237 | SECCHI Surv Pwr OFF, Op Pwr ON, Decontam Htr ON, Interface Htr OFF | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04.
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | 315 | -- | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
C&DH | Playback G&C Blackbox Data | 315 | -- | 2 min | 360 | 245 | Macro 427. Start before enabling GT use in next event | MOps Script Rev, 8/3/06
3.2/3.2/93/2/0/3.3
SECCHI G&C | 1st GT Calibration (1st Enabling of GT Use) – AHEAD only | 315 | -- | 1.5 hrs | 360 | 245 | Playback SSR using macro 427 until G&C blackbox data is played back, Configure G&C Blackbox for APIDs: 14F (Standby pkt) @ 1/second, 14C (GT Raw Messages @ 250 Hz) @ 7/second, 152 (RTW Output of Y and Z sung’s) @ 2/second, Enable GT use, Switch G&C TLM to nominal after 1.5 hours. Planning - use secchi_gt_cal.sch template and schedule as UT to occur during the track. | SECCHI Ops Lead email, 7/18/06 SECCHI GT Lead email, 8/29/06
3.2/3.2/93/2/0/3.3
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 315 | -- | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
RF | Step HGARA | 316 | 316 | 5 min | 360 | 237 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
SECCHI | Crack open EUVI, COR1, & COR2 doors. | 316 | 316 | 20 min | 360 | 237 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
3.2/3.2/3.6/2.2/0.6/3.3
S/C | A2 Backup Delta V Maneuver | 317 | 317 | 4 hrs | 96 | 234 | Non-deterministic. Only if prime maneuver was not successful. | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | -- | 317 | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
C&DH | Playback G&C Blackbox Data | -- | 317 | 2 min | 360 | 245 | Macro 427. Start before enabling GT use in next event | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI G&C | 1st GT Calibration (1st Enabling of GT Use) – BEHIND only | -- | 317 | 1.5 hrs | 360 | 245 | Playback SSR using macro 427 until G&C blackbox data is played back, Configure G&C Blackbox for APIDs: 14F (Standby pkt) @ 1/second, 14C (GT Raw Messages @ 250 Hz) @ 7/second, 152 (RTW Output of Y and Z sung’s) @ 2/second, Enable GT use, Switch G&C TLM to nominal after 1.5 hours. Planning - use secchi_gt_cal.sch template and schedule as UT to occur during the track. | SECCHI Ops Lead email, 7/18/06 SECCHI GT Lead email, 8/29/06
3.2/3.2/93/2/0/3.3
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | -- | 317 | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
PLASTIC | MCP HV on to low Op levels – Day 1 | 317 | 317 | 2 hrs | 360 | 237 | Need RT cmd & TLM | PLASTIC-Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
IMPACT | Power-up and checkout SEP and STE - Day 1 | 317 | 317 | 3 hrs | 360 | 237 | IMPACT SEP/SEPT2 Surv Pwr OFF, Op Pwr ON, Interface Htr (2) OFF | IMPACT CDR, 11/22/02. TLM and SSR usage per lead worksheet 2-17-2004. STE c/o added M-O-R 11/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Macro 496
IMPACT | SEP and STE Checkout – Day 2 | 318 | 318 | 3 hrs | 360 | 237 |  | IMPACT CDR, 11/22/02. TLM and SSR usage per lead worksheet 2-17-2004
3.2/3.2/3.6/2.2/0.6/3.3
PLASTIC | MCP HV on to low Op levels – Day 2 | 318 | 318 | 2 hrs | 360 | 237 | Need RT cmd & TLM | PLASTIC-Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
IMPACT | SEP and STE Checkout – Day 3 | 319 | 319 | 3 hrs | 360 | 237 |  | IMPACT CDR, 11/22/02. TLM and SSR usage per lead worksheet 2-17-2004
3.2/3.2/3.6/2.2/0.6/3.3
RF | Step HGARA | 320 | 320 | 5 min | 360 | 237 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
PLASTIC | MCP HV on to low Op levels – Day 3 | 320 | 320 | 2 hrs | 360 | 237 | Need RT cmd & TLM | PLASTIC-Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
***** | AOS DSN Track – Pre-Maneuver
SECCHI | Close COR1, COR2, & EUVI doors | 321 | 321 | 20 min | 360 | 237 | SECCHI reclosable doors are not grounded and could arc while passing through the radiation belts. | System Eng Lead email, 5/15/03
3.2/3.2/3.6/2.2/0.6/3.3
G&C | Disable GT Use | 321 | 321 | 2 min | 360 | 237 | Script: ahead_secchi_gt_pointing_disable.prc | G&C phone call 8/5/05
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Switch OFF SECCHI Operational Power | 321 | 321 | 5 min | 360 | 237 | SECCHI Surv Pwr ON, Op Pwr OFF, Interface Htr Off | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04.
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Decontamination Power to remain ON.
C&DH | Abort SECCHI Decontamination Heater Duty Cycling Macro | 321 | 321 | 2 min | 360 | 237 | Abort relative TT #6 and #7 | System Lead email, 2/10/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | SECCHI Decon. Heater Pwr OFF
6 hrs before delta V maneuver
Script: secchi_decon_heater_stick_off.prc
SWAVES, PLASTIC IMPACT | Power down before P2 Maneuver | 321 | 321 | 10 min | 360 | 237 | If needed. Baseline instru. off during maneuvers due to power limitations. PLASTIC OFF prior to IMPACT IDPU OFF. SWAVES off last. IMPACT MAG Htr Enabled, Boom Htr & Op Pwr OFF | SRD. PLASTIC-Ops WGM 4/21/04. . SWAVES - MOR D-R #2 10/28/04. DAO email 7/8/05
|  |  |  | 30 min - PLASTIC | 3.2/3.2/3.6/2.2/0.6/3.3 |  | IMPACT SWEA/STE Surv Pwr ON, Op Pwr OFF
IMPACT SEP/SEPT2 Surv Pwr ON, Op Pwr OFF, Interface Htr (2) OFF
PLASTIC Surv Pwr ON, Op Pwr OFF
SECCHI Surv Pwr ON, Op Pwr OFF, Interface Htr Off, SWAVES Op Pwr OFF, Replacement Htr ON
***** | AOS DSN Track – Maneuver
C&DH | Change to RTDFD 234 - 96 kbps - Delta V maneuvers, S/C & Instruments | 321 | 321 | 2 min | 96 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/26.1
S/C | P2 Delta V Maneuver | 321 | 321 | 4 hrs | 96 | 234 | Deterministic. | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 321 | 321 | 2 min | 360 | 237 | Macro 213. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Start SSR Playback | 321 | 321 | 2 min | 360 | 237 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ssr_playback_enable.prc
***** | AOS DSN Track – Post Maneuver
SWAVES | Power and recover SWAVES, IMPACT, and PLASTIC from P2 Maneuver | 321 | 321 | 1 hr | 360 | 237 | If needed. IMPACT IDPU/MAG power-up first, then SWAVES. IDPU, SWEA/STE-D, & SEP for IMPACT. PLASTIC ON after IMPACT IDPU | SRD. SWAVES - MOR D-R #2 10/28/04. DAO email 7/8/05. IMPACT Lead email 8/15/05.
IMPACT |  |  |  |  | 3.2/3.2/3.6/2.2/0.6/3.3 |  | IMPACT MAG Htr Enabled, Boom Htr OFF, & IDPU Op Pwr ON
PLASTIC | [6 empty] | IMPACT SWEA/STE Surv Pwr OFF, Op Pwr ON
IMPACT SEP/SEPT2 Surv Pwr OFF, Op Pwr ON, Interface Htr (2) OFF
PLASTIC Surv Pwr ON, Op Pwr ON
SWAVES Op Pwr ON, Replacement Htr OFF.
IMPACT: ramp up SWEA HV, configure SEP, and ramp up SIT HVPS (~15 minutes.)
SECCHI | Enable MOps SECCHI Decontamination Heater Duty Cycling Macro | 321 | 321 | 2 min | 360 | 237 | Use duty cycle 65 seconds on and 55 seconds off in macro 492 & 493 | Systems Eng, 5/26/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | 6 hrs after delta V maneuver
Script: secchi_decon_htr_on.prc
SECCHI | Power ON SECCHI Operational Power | 321 | 321 | 20 min | 360 | 237 | SECCHI Surv Pwr OFF, Op Pwr ON, Decontam Htr ON, Interface Htr OFF | Obs PDR, 12/5/01, SECCHI Telecon 1/23/04
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | 321 | 321 | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
G&C | Enable GT Use | 321 | 321 | 10 min | 360 | 245 | Collect G&C GT performance data | G&C phone call 8/8/05
[5 empty] | 3.2/3.2/93/2.2/0.6/3.3 |  | Script: ahead_secchi_gt_pointing_enable.prc
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 321 | 321 | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
PLASTIC | Recover from P2.PAC to 5kV, SSDs ON, the Pac to 10kV, MCPs ON (1 of 3) | 321 | 321 | 3 hrs | 360 | 237 |  | PLASTIC-Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Crack open EUVI, COR1, & COR2 doors. | 322 | 322 | 20 min | 360 | 237 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
3.2/3.2/3.6/2.2/0.6/3.3
PLASTIC | Recover from P2.PAC to 5kV, SSDs ON, the Pac to 10kV, MCPs ON (2 of 3) | 322 | 322 | 3 hrs | 360 | 237 |  | PLASTIC-Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
PLASTIC | Recover from P2.PAC to 5kV, SSDs ON, the Pac to 10kV, MCPs ON (3 of 3) | 323 | 323 | 3 hrs | 360 | 237 |  | PLASTIC-Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
RF | Step HGARA | 324 | 324 | 5 min | 360 | 237 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
***** | AOS Next DSN Track
G&C | Disable GT Use | 326 | 326 | 2 min | 360 | 237 | Script: ahead_secchi_gt_pointing_disable.prc | G&C phone call 8/5/05
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Close COR1, COR2, & EUVI doors | 326 | 326 | 20 min | 360 | 237 | SECCHI reclosable doors are not grounded and could arc while passing through the radiation belts. | System Eng Lead email, 5/15/03
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Switch OFF SECCHI Operational Power | 326 | 326 | 5 min | 360 | 237 | SECCHI Surv Pwr ON, Op Pwr OFF, Decontam Htr OFF, Interface Htr OFF | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04.
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Abort SECCHI Decontamination Heater Duty Cycling Macro | 326 | 326 | 2 min | 360 | 237 | Abort relative TT #6 and #7 | System Lead email, 2/10/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | SECCHI Decon. Heater Pwr OFF
6 hrs before delta V maneuver
Script: secchi_decon_heater_stick_off.prc
SWAVES, PLASTIC IMPACT | Power down before A3 through P3 Maneuver | 326 | 326 | 10 min | 360 | 237 | If needed. Baseline instru. off during maneuvers due to power limitations. PLASTIC OFF prior to IMPACT IDPU OFF. SWAVES off last. IMPACT MAG Htr Enabled, Boom Htr & Op Pwr OFF | SRD. PLASTIC-Ops WGM 4/21/04. . SWAVES - MOR D-R #2 10/28/04. DAO email 7/8/05
|  |  |  | 30 min. PLASTIC | 3.2/3.2/3.6/2.2/0.6/3.3 |  | IMPACT SWEA/STE Surv Pwr ON, Op Pwr OFF
IMPACT SEP/SEPT2 Surv Pwr ON, Op Pwr OFF, Interface Htr (2) OFF
PLASTIC Surv Pwr ON, Op Pwr OFF
SWAVES Op Pwr OFF, Replacement Htr ON, Abort Timetags 6 & 7 and SECCHI Decon. Heater Pwr OFF
***** | AOS DSN Track – Maneuver
C&DH | Change to RTDFD 234 - 96 kbps - Delta V maneuvers, S/C & Instruments | 326 | 326 | 2 min | 96 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/26.1
S/C | A3 Prime Delta V Maneuver | 326 | 326 | 4 hrs | 96 | 234 | Non-deterministic | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 326 | 326 | 2 min | 360 | 237 | Macro 213. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Start SSR Playback | 326 | 326 | 2 min | 360 | 237 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ssr_playback_enable.prc
SECCHI | Enable MOps SECCHI Decontamination Heater Duty Cycling Macro | 326 | 326 | 2 min | 360 | 237 | Use duty cycle 65 seconds on and 55 seconds off in macro 492 & 493 | Systems Eng, 5/26/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | 6 hrs after delta V maneuver
Script: secchi_decon_htr_on.prc
IMPACT G&C RF | 1st four, 15 deg/min rolls about X-axis to calibrate MAG DC offsets with HGA end-to-end slews - AHEAD only | 326 | -- | 2 hrs | 360 | 237 | During a DSN track | SRR, 5/24/00. TLM and SSR usage per lead worksheet 2-17-2004
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Post A3 if no maneuver. Test S/C continuous roll. Need to switch LGAs to maintain communications. Schedule when system momentum is low. | SSC Lead email, 6/7/06
Script: earlyops_mag_smooth_cal.prc
IMPACT RF | 1st HGA end-to-end slew for MAG calibration - AHEAD only | 326 | -- | 10 min | 360 | 237 | MAG team also needs the HGA to slew from 0 to 180 (3 minutes) after the roll. Slew limited to < 5 minutes due to thermal damage constraint 2.2.1. Disable autonomy rule 25 (Monitor HGA health) before each test. | MAG email, 2/15/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: earlyops_hga_slew_to_180.prc | SSC Lead email, 6/7/06
IMPACT G&C RF | 1st four, 15 deg/min rolls about X-axis to calibrate MAG DC offsets with HGA end-to-end slews – BEHIND only | -- | 326 | 2 hrs | 360 | 237 | During a DSN track | SRR, 5/24/00. TLM and SSR usage per lead worksheet 2-17-2004
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Post A3 if no maneuver. Test S/C continuous roll. Need to switch LGAs to maintain communications. Schedule when system momentum is low. | SSC Lead email, 6/7/06
Script: earlyops_mag_smooth_cal.prc
IMPACT RF | 1st HGA end-to-end slew for MAG calibration - BEHIND only | -- | 326 | 10 min | 360 | 237 | MAG team also needs the HGA to slew from 0 to 180 (3 minutes) after the roll. Slew limited to < 5 minutes due to thermal damage constraint 2.2.1. Disable autonomy rule 25 (Monitor HGA health) before each test. | MAG email, 2/15/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: earlyops_hga_slew_to_180.prc | SSC Lead email, 6/7/06
RF | Step HGARA | 328 | 328 | 5 min | 360 | 237 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
***** | Week 48
C&DH | Abort SECCHI Decontamination Heater Duty Cycling Macro | 331 | 331 | 2 min | 360 | 237 | On L+ 33 days | System Lead email, 2/10/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Abort relative TT #6 and #7
Script: secchi_decon_heater_stick_off.prc
RF | Step HGARA | 332 | 332 | 5 min | 360 | 237 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
C&DH | Change to RTDFD 234 - 96 kbps - Delta V maneuvers, S/C & Instruments | 333 | 333 | 2 min | 96 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/26.1
RF | HGA Auto Track Test | 333 | 333 | 2 hrs | 96 | 234 | Test HGA auto track while SPE angle is changing. | HGA Auto Track mtg, 11/21/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Script: TBD
S/C | P3 Delta V Maneuver | 333 | 333 | 4 hrs | 96 | 234 | Non-deterministic | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 333 | 333 | 2 min | 360 | 237 | Macro 213. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Start SSR Playback | 333 | 333 | 2 min | 360 | 237 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ssr_playback_enable.prc
***** | AOS DSN Track – Post P3 Maneuver/Eclipse Recovery
| Power and recover SWAVES, IMPACT, and PLASTIC from A3 through P3 Maneuvers. | 333 | 333 | 1 hr |  | 237 | If needed. SWAVES power-up first. IDPU, SWEA/STE-D, & SEP for IMPACT. PLASTIC ON after IMPACT IDPU | SRD. PLASTIC-Ops WGM 4/21/04. SWAVES - MOR D-R #2 10/28/04. DAO email 7/8/05. IMPACT lead email 8/15/05.
IMPACT MAG Htr Enabled, Boom Htr OFF, & IDPU Op Pwr ON
SWAVES IMPACT |  |  |  |  | 360 |  | IMPACT SWEA/STE Surv Pwr OFF, Op Pwr ON
PLASTIC |  |  |  |  | 3.2/3.2/3.6/2.2/0.6/3.3 |  | IMPACT SEP/SEPT2 Surv Pwr OFF, Op Pwr ON, Interface Htr (2) OFF
PLASTIC Surv Pwr ON, Op Pwr ON
SWAVES Op Pwr ON, Replacement Htr OFF.
IMPACT: ramp up SWEA HV, configure SEP, and ramp up SIT HVPS (~15 minutes.)
SECCHI | Power ON SECCHI Operational Power | 333 | 333 | 20 min | 360 | 237 | SECCHI Surv Pwr OFF, Op Pwr ON, Decontam Htr OFF, Interface Htr OFF | Obs PDR, 12/5/01, SECCHI Telecon 1/23/04
3.2/3.2/3.6/2.2/0.6/3.3
IMPACT G&C RF | 2nd four, 15 deg/min rolls about X-axis to calibrate MAG DC offsets with HGA end-to-end slews - AHEAD only | 333 | -- | 2 hrs | 360 | 237 | During a DSN track | SRR, 5/24/00. TLM and SSR usage per lead worksheet 2-17-2004
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Desire region within the Earth's magnetosphere where the magnetic field is high but "smooth", i.e., altitude < 50,000 km (± 3 hrs of perigee). Schedule when system momentum is low. | SSC Lead email, 6/7/06
Script: earlyops_mag_smooth_cal.prc
IMPACT RF | 2nd HGA end-to-end slew for MAG calibration - AHEAD only | 333 | -- | 10 min | 360 | 237 | MAG team also needs the HGA to slew from 180 to 0 (3 minutes) after the roll. Slew limited to < 5 minutes due to thermal damage constraint 2.2.1. Disable autonomy rule 25 (Monitor HGA health) before each test. | MAG email, 2/15/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: earlyops_hga_slew_to_0.prc | SSC Lead email, 6/7/06
IMPACT G&C RF | 2nd four, 15 deg/min rolls about X-axis to calibrate MAG DC offsets with HGA end-to-end slews – BEHIND only | -- | 333 | 2 hrs | 360 | 237 | During a DSN track | SRR, 5/24/00. TLM and SSR usage per lead worksheet 2-17-2004
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Desire region within the Earth's magnetosphere where the magnetic field is high but "smooth", i.e., altitude < 50,000 km (± 3 hrs of perigee). Schedule when system momentum is low. | SSC Lead email, 6/7/06
Script: earlyops_mag_smooth_cal.prc
IMPACT RF | 2nd HGA end-to-end slew for MAG calibration - BEHIND only | -- | 333 | 10 min | 360 | 237 | MAG team also needs the HGA to slew from 180 to 0 (3 minutes) after the roll. Slew limited to < 5 minutes due to thermal damage constraint 2.2.1. Disable autonomy rule 25 (Monitor HGA health) before each test. | MAG email, 2/15/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: earlyops_hga_slew_to_0.prc | SSC Lead email, 6/7/06
SECCHI | Perform SECCHI Camera Readouts of Dark Images & calibration lamp exposures (1 of 3) - (UT event) | 333 | 333 | 2 hrs | NA | NA | SECCHI only UT event | SECCHI CDR, 11/6/02, SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04.
NA
SECCHI | Mechanical Tuning Test (1 of 3) | 333 | 333 | 3 hrs | 360 | 237 |  | Early Ops Rev, 5/31/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | 333 | 333 | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
G&C | Enable GT Use | 333 | 333 | 10 min | 360 | 245 | Collect G&C GT performance data | G&C phone call 8/8/05
[5 empty] | 3.2/3.2/93/2.2/0.6/3.3 |  | Script:secchi_gt_pointing_enable.prc
G&C | Switch G&C TLM Schedule | 333 | 333 | 10 min | 360 | 245 | Collect G&C GT performance data. Change to the following schedule for 10 minutes and then back to nominal: Standby mode = 1/sec, Gyro Data @ 100 Hz = 3/sec, RTW Output of Y and Z sung's and GT status = 3/sec, Wheel torques @ 50 Hz = 2/sec, Standby mode = 1/sec | G&C email, 11/15/06
[5 empty] | 3.2/3.2/93/2.2/0.6/3.3 |  | Script: gc_tlm_sched_inst_cal.prc
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 333 | 333 | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
PLASTIC | PAC to 10kV then 15 (1 of 3) | 334 | 334 | 2-3 hrs | 360 | 237 |  | PLASTIC-Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Perform SECCHI Camera Readouts of Dark Images & calibration lamp exposures (2 of 3) - (UT event) | 334 | 334 | 2 hrs | NA | NA | SECCHI only UT event | SECCHI CDR, 11/6/02, SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04.
NA
SECCHI | Mechanical Tuning Test (2 of 3) | 334 | 334 | 3 hrs | 360 | 237 |  | Early Ops Rev, 5/31/06
3.2/3.2/3.6/2.2/0.6/3.3
PLASTIC | Complete recovery from A3+ and P3 Maneuvers. PLASTIC HV to 10kV, then 15kV, SSD bias V on, increase MCP HV to Op level. | 334 | 334 | 3 hrs | 360 | 237 |  | Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Perform SECCHI Camera Readouts of Dark Images & calibration lamp exposures (3 of 3) - (UT event) | 335 | 335 | 2 hrs | NA | NA | SECCHI only UT event | SECCHI CDR, 11/6/02, SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04.
NA
SECCHI | Mechanical Tuning Test (3 of 3) | 335 | 335 | 3 hrs | 360 | 237 |  | Early Ops Rev, 5/31/06
3.2/3.2/3.6/2.2/0.6/3.3
PLASTIC | PAC to 10kV then 15 (2 of 3) | 335 | 335 | 2-3 hrs | 360 | 237 |  | PLASTIC-Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
***** | Saturday
RF | Step HGARA | 336 | 336 | 10 min | 360 | 245 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days. SECCHI requested 93 kbps during the HGARA stepping for 10 min | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/93/2.2/0.6/3.3 |  | Script: hgara_step.prc
PLASTIC | PAC to 10kV then 15 (3 of 3) | 336 | 336 | 2-3 hrs | 360 | 237 |  | PLASTIC-Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
***** | Sunday
PLASTIC | PLASTIC HV to 10kV, then 15kV, SSD bias V on, increase MCP HV to Op level | 337 | 337 | 3 hrs | 360 | 237 |  | SRD. PLASTIC-Ops WGM 4/21/04.
3.2/3.2/3.6/2.2/0.6/3.3
***** | Week 49
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | 338 | -- | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI | Open EUVI, COR1, & COR2 doors - AHEAD only | 338 | -- | 20 min | 360 | 245 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
3.2/3.2/93/2/0/3.3
SECCHI | COR1, COR2, and EUVI First Light - AHEAD only | 338 | -- |  | 360 | 245 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
|  |  |  | 2 hrs | 3.2/3.2/93/2/0/3.3
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 338 | -- | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | 340 | -- | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI G&C | 2nd GT Calibration – AHEAD only | 340 | -- | 1.5 hrs | 360 | 245 | SECCHI-driven offpoints up to 40 arc seconds. Configure G&C Blackbox for APIDs: 14F (Standby pkt) @ 1/second, 14C (GT Raw Messages @ 250 Hz) @ 7/second, 152 (RTW Output of Y and Z sung’s) @ 2/second, Enable GT use, Switch G&C TLM to nominal after 1.5 hous. Planning - use secchi_gt_cal.sch template and schedule as UT to occur during the track. | SECCHI Ops Lead email, 7/18/06, 10/13/06, SECCHI GT Lead email, 8/29/06
3.2/3.2/93/2.2/0.6/3.3
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 340 | -- | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
***** | AOS Next DSN Track
RF | Step HGARA | 340 | 340 | 5 min | 360 | 237 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
G&C | Disable GT Use | -- | 340 | 2 min | 360 | 237 | Script: ahead_secchi_gt_pointing_disable.prc | G&C phone call 8/5/05
3.2/3.2/3.6/2.2/0.6/3.3
***** | AOS DSN Track – Maneuver
C&DH | Change to RTDFD 234 - 96 kbps - Delta V maneuvers, S/C & Instruments | -- | 340 | 2 min | 96 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/26.1
S/C | A4 Prime Delta V Maneuver | -- | 340 | 4 hrs | 96 | 234 | Non-deterministic | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | -- | 340 | 2 min | 360 | 237 | Macro 213. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Start SSR Playback | -- | 340 | 2 min | 360 | 237 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ssr_playback_enable.prc
***** | AOS DSN Track – Post Maneuver
S/C | A4 Backup Delta V Maneuver | 341 | 341 | 4 hrs | 96 | 234 | Non-deterministic. Only if prime maneuver was not successful. | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
S/C | Start Space Weather broadcast post-track | 341 | 341 | 21 hrs | 0/0/0/0/0.6/0 | 225 | Post A4. | RF Lead email, 9/12/03
Macro 205. Configure for space weather data rate, 633 bps, conv r=1/6 for non-DSN time. Pc/NO will decrease by 9 dB-Hz for space weather data rate.
PLASTIC | Complete recovery from A4 Maneuver. MCPs to ops. Turn on Entrance system. | 341 | 341 | 3 hrs | 360 | 237 |  | Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
RF | HGA Checkout and Calibration #1 | 342 | 342 | 2 hrs | 360 | 237 | Post A4 | RF email, 3/4/04. DAO email 8/3/05.
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Earth range > 175,000 km
Need DSN track
Use 360 kbps, biphase-L, turbo encoding, ranging on
Desire GT on
SPE angle = 137 deg (AHEAD).
SPE angle = 137 deg (BEHIND)
Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
PLASTIC | Complete recovery from A4 Maneuver. MCPs to ops. | 342 | 342 | 3 hrs | 360 | 237 |  | Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
***** | Saturday
PLASTIC | Complete recovery from A4 Maneuver. MCPs to ops. | 343 | 343 | 3 hrs | 360 | 237 |  | Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
IMPACT | SIT HVPS power-up and checkout. SEP and STE Checkout – Day 1 of 5 | 343 | 343 | 3 hrs | 360 | 237 | Need 5 continuous days without thruster firing. Individual instrument testing will be done in parallel. | IMPACT Ops Lead email, 7/20/06
3.2/3.2/3.6/2.2/0.6/3.3
***** | Sunday
PLASTIC | ESA, S-channel, and DEFL checkouts | 344 | 345 | 3 hrs | 360 | 237 | Need RT cmding | PLASTIC PDR, 9/25/02. Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
IMPACT | SIT HVPS power-up and checkout. SEP and STE Checkout – Day 2 of 5 | 344 | 344 | 3 hrs | 360 | 237 | Need 5 continuous days without thruster firing. Individual instrument testing will be done in parallel. | IMPACT CDR, 11/22/02. TLM and SSR usage per lead worksheet 2-17-2004. IMPACT lead email 9/1/05
3.2/3.2/3.6/2.2/0.6/3.3
***** | Week 50
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | 345 | -- | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI | Open HI Baffle Cover Door | 345 | -- | 15 min | 360 | 245 | Enable rule 70 (HI wax actuator protection) before starting. 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
| (Spacecraft-Commanded) - AHEAD only |  |  |  | 3.2/3.2/93/2/0/3.3 |  | Dependent on all maneuvers being completed
Script: secchi_hi_cover_deploy.prc
SECCHI | HI-1 and HI-2 First Light - AHEAD only | 345 | -- | 2 hrs | 360 | 245 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
[5 empty] | 3.2/3.2/93/2/0/3.3 |  | Dependent on all maneuvers being completed
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 345 | -- | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
PLASTIC | ESA, S-channel, and DEFL checkouts | 345 | 345 | 3 hrs | 360 | 237 | Need RT cmding | PLASTIC PDR, 9/25/02. Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
IMPACT | SIT HVPS power-up and checkout. SEP and STE Checkout – Day 3 of 5 | 345 | 345 | 3 hrs | 360 | 237 | Need 5 continuous days without thruster firing. Individual instrument testing will be done in parallel. | IMPACT CDR, 11/22/02. TLM and SSR usage per lead worksheet 2-17-2004. IMPACT lead email 9/1/05
3.2/3.2/3.6/2.2/0.6/3.3
RF | Step HGARA | 344 | 344 | 5 min | 360 | 237 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
IMPACT | SIT HVPS power-up and checkout. SEP and STE Checkout – Day 4 of 5 | 346 | 346 | 3 hrs | 360 | 237 | Need 5 continuous days without thruster firing. Individual instrument testing will be done in parallel. | IMPACT CDR, 11/22/02. TLM and SSR usage per lead worksheet 2-17-2004. IMPACT lead email 9/1/05
3.2/3.2/3.6/2.2/0.6/3.3
IMPACT | SIT HVPS power-up and checkout. SEP and STE Checkout – Day 5 of 5 | 347 | 347 | 3 hrs | 360 | 237 | Need 5 continuous days without thruster firing. Individual instrument testing will be done in parallel. | IMPACT CDR, 11/22/02. TLM and SSR usage per lead worksheet 2-17-2004. IMPACT lead email 9/1/05
3.2/3.2/3.6/2.2/0.6/3.3
S/C | Stop Space Weather broadcast post-track | 346 | 346 |  | 360 | 237 | P4 – 1 day | RF Lead email, 9/12/03
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Space weather cannot be transmitted on the LGA below 61,000 km altitude due to PFD limits violations.
***** | AOS Next DSN Track
G&C | Disable GT Use | 346 | 346 | 2 min | 360 | 237 | Script: ahead_secchi_gt_pointing_disable.prc | G&C phone call 8/5/05
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Close COR1, COR2, & EUVI doors – AHEAD only | 346 | -- | 20 min | 360 | 237 | SECCHI reclosable doors are not grounded and could arc while passing through the radiation belts. | System Eng Lead email, 5/15/03
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Verify COR1, COR2, & EUVI doors closed – BEHIND only | -- | 346 | 5 min | 360 | 237 | SECCHI reclosable doors are not grounded and could arc while passing through the radiation belts. | System Eng Lead email, 5/15/03
3.2/3.2/3.6/2.2/0.6/3.3
***** | AOS DSN Track – Maneuver
C&DH | Change to RTDFD 234 - 96 kbps - Delta V maneuvers, S/C & Instruments | 346 | 346 | 2 min | 96 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/26.1
S/C | P4 Delta V Maneuver | 346 | 346 | 4 hrs | 96 | 234 | Non-deterministic | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 346 | 346 | 2 min | 360 | 237 | Macro 213. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Start SSR Playback | 346 | 346 | 2 min | 360 | 237 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ssr_playback_enable.prc
***** | AOS DSN Track – Post Maneuver
IMPACT G&C RF | 3rd four, 15 deg/min rolls about X-axis to calibrate MAG DC offsets with HGA end-to-end slews - AHEAD only | 346 | -- | 2 hrs | 360 | 237 | During a DSN track | SRR, 5/24/00. TLM and SSR usage per lead worksheet 2-17-2004
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Desire region within the Earth's magnetosphere where the magnetic field is high but "smooth", i.e., altitude < 50,000 km (± 3 hrs of perigee). Schedule when system momentum is low. | SSC Lead email, 6/7/06
Script: earlyops_mag_smooth_cal.prc
IMPACT RF | 3rd HGA end-to-end slew for MAG calibration - AHEAD only | 346 | -- | 10 min | 360 | 237 | MAG team also needs the HGA to slew from 180 to 0 (3 minutes) after the roll. Slew limited to < 5 minutes due to thermal damage constraint 2.2.1. Disable autonomy rule 25 (Monitor HGA health) before each test. | MAG email, 2/15/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: earlyops_hga_slew_to_0.prc | SSC Lead email, 6/7/06
IMPACT G&C RF | 3rd four, 15 deg/min rolls about X-axis to calibrate MAG DC offsets with HGA end-to-end slews – BEHIND only | -- | 346 | 2 hrs | 360 | 237 | During a DSN track | SRR, 5/24/00. TLM and SSR usage per lead worksheet 2-17-2004
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Desire region within the Earth's magnetosphere where the magnetic field is high but "smooth", i.e., altitude < 50,000 km (± 3 hrs of perigee). Schedule when system momentum is low. | SSC Lead email, 6/7/06
Script: earlyops_mag_smooth_cal.prc
IMPACT RF | 3rd HGA end-to-end slew for MAG calibration - BEHIND only | -- | 346 | 10 min | 360 | 237 | MAG team also needs the HGA to slew from 180 to 0 (3 minutes) after the roll. Slew limited to < 5 minutes due to thermal damage constraint 2.2.1. Disable autonomy rule 25 (Monitor HGA health) before each test. | MAG email, 2/15/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: earlyops_hga_slew_to_0.prc | SSC Lead email, 6/7/06
G&C | Enable GT Use | 346 | 346 | 2 min | 360 | 237 | Collect G&C GT performance data | G&C phone call 8/8/05
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ahead_secchi_gt_pointing_enable.prc
PLASTIC | Recover from P4 Maneuver (first of 2 days) | 346 | 346 | 3 hrs | 360 | 237 |  | Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | -- | 347 | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI | Open EUVI, COR1, & COR2 doors – BEHIND only | -- | 347 | 20 min | 360 | 245 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
3.2/3.2/93/2/0/3.3
SECCHI | COR1, COR2, and EUVI First Light – BEHIND only | -- | 347 |  | 360 | 245 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
|  |  |  | 2 hrs | 3.2/3.2/93/2/0/3.3
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | -- | 347 | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
***** | Switch from 3 hour track DSN coverage to 4 hour tracks centered every 24 hours – AHEAD only | 347 | NA
SECCHI | Fully open EUVI, COR1, & COR2 doors. - AHEAD only | 347 | -- | 20 min | 360 | 237 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
3.2/3.2/3.6/2.2/0.6/3.3
IMPACT | Deploy SIT and SEPT covers - AHEAD only | 347 | -- | 3 hrs | 360 | 237 | SEPT-NS and SEPT-E each have two covers. | IMPACT Lead email 4/29/03. TLM and SSR usage per lead worksheet 2-17-2004
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: impact_sept_cover_deploy.prc
S/C | Start Space Weather broadcast post-track | 347 | 347 | 21 hrs | 0/0/0/0/0.6/0 | 225 | P4+ 1 day | RF Lead email, 9/12/03
When altitude > 61,000 km.
Macro 205. Configure for space weather data rate, 633 bps, conv r=1/6 for non-DSN time. Pc/NO will decrease by 9 dB-Hz for space weather data rate.
PLASTIC | Recover from P4 Maneuver | 347 | 347 | 3 hrs | 360 | 237 |  | Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
IMPACT | SEPT Instruments commissioning - AHEAD only | 347 | -- | 3 hrs | 360 | 237 |  | IMPACT Lead email 1/9/04. TLM and SSR usage per lead worksheet 2-17-2004
3.2/3.2/3.6/2.2/0.6/3.3
RF | Step HGARA – BEHIND only | -- | 348 | 5 min | 360 | 237 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
C&DH | Change to RTDFD 234 - Delta V maneuvers, S/C & Instruments, 3.2/3.2/3.6/2.2/0.6/26.1 | 349 | 349 | 2 min | 360 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. Set PB ratio to 8 | G&C Lead email, 5/19/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Script: rtdfd14_pb17.prc
S/C | S1 – First Lunar Swingby | 349 | 349 | 4 hrs | 360 | 234 | AHEAD DV = 756 m/sec | Mission Design, 8/8/2006
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | AHEAD Altitude = 7,340 km
BEHIND Altitude = 11,776 km
BEHIND DV = 602 m/sec
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments, 3.2/3.2/3.6/2.2/0.6/3.3, Phasing Orbit | 349 | 349 | 2 min | 360 | 237 | Macro 237
3.2/3.2/3.6/2.2/0.6/3.3
***** | Saturday
SECCHI G&C | 2nd GT Calibration (UT event) – BEHIND only | -- | 350 | 1.5 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Configure G&C Blackbox for APIDs: 14F (Standby pkt) @ 1/second, 14C (GT Raw Messages @ 250 Hz) @ 7/second, 152 (RTW Output of Y and Z sung’s) @ 2/second, Enable GT use, Switch G&C TLM to nominal after 1.5 hous | SECCHI Ops Lead email, 7/18/06 SECCHI GT Lead email, 8/29/06
PLASTIC | Observe simultaneous A/B science data for inter-calibration | 350 | 350 | 3 hrs | 360 | 237 | Daily contacts for data. As much as possible. | PLASTIC Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
S1+1 day
G&C | Enable RW Speed Avoidance Algorithm | 350 | 350 | 2 min | 360 | 237 | Default for RW speed avoidance algorithm is disabled. (GCC.Ctl.SpeedAvoid=1) | C. Ray email, 4/27/05
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script:
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | 350 | 350 | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
G&C | RW Effects on Jitter | 350 | 350 | 2 hrs | 360 | 245 | Ramp-up/down RWs | G&C Lead, 6/18/03
[5 empty] | 3.2/3.2/93/2/0/3.3 |  | Script:
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 350 | 350 | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
***** | Week 51 – BEHIND only
S1+1 day
G&C | Enable RW Speed Avoidance Algorithm | 353 | 351 | 2 min | 360 | 237 | Default for RW speed avoidance algorithm is disabled. (GCC.Ctl.SpeedAvoid=1) | C. Ray email, 4/27/05
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script:
C&DH | Change to RTDFD 245 - 360 kbps - Days 11 & others | 353 | 351 | 2 min | 360 | 245 | Macro 245. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
G&C | RW Effects on Jitter | 353 | 351 | 2 hrs | 360 | 245 | Ramp-up/down RWs | G&C Lead, 6/18/03
[5 empty] | 3.2/3.2/93/2/0/3.3 |  | Script:
C&DH | Change to RTDFD 237 - 360 kbps - S/C, Nominal Instruments | 353 | 351 | 2 min | 360 | 237 | Macro 237. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
RF | Step HGARA – BEHIND only | -- | 352 | 5 min | 360 | 237 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
SWAVES | 1st SWAVES Smooth Calibration Rolls (UT event) - BEHIND only | -- | 353 | 10 hrs | NA | NA | Timetagged event (UT). Execute when system momentum is low, between 640,000 & 900,000 km, & to end 30 minutes before BOT due to G&C blackbox limitations. | SSC Lead email, 6/21/06
***** | AOS Next DSN Track
G&C | Disable GT Use – BEHIND only | -- | 355 | 2 min | 720 | 241 | Script: ahead_secchi_gt_pointing_disable.prc | G&C phone call 8/5/05
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Close COR1, COR2, & EUVI doors – BEHIND only | -- | 355 | 20 min | 720 | 241 |  | System Eng Lead email, 5/15/03
3.2/3.2/3.6/2.2/0.6/3.3
***** | AOS DSN Track – Maneuver
C&DH | Change to RTDFD 234 - 96 kbps - Delta V maneuvers, S/C & Instruments | -- | 355 | 2 min | 96 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/26.1
S/C | S1+ Prime Delta V Maneuver- BEHIND only | -- | 355 | 4 hrs | 96 | 234 | Non-deterministic | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Change to RTDFD 241 - 720 kbps - S/C, Nominal Instruments | -- | 355 | 2 min | 720 | 241 | Macro 216. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Start SSR Playback | -- | 355 | 2 min | 720 | 241 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ssr_playback_enable.prc
***** | AOS DSN Track – Post Maneuver
G&C | Enable GT Use – BEHIND only | -- | 355 | 2 min | 720 | 241 | Collect G&C GT performance data | G&C phone call 8/8/05
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ahead_secchi_gt_pointing_enable.prc
SECCHI G&C | 3rd GT Calibration (UT event) – BEHIND only | -- | 355 | 1.5 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Configure G&C Blackbox for APIDs: 14F (Standby pkt) @ 1/second, 14C (GT Raw Messages @ 250 Hz) @ 7/second, 152 (RTW Output of Y and Z sung’s) @ 2/second, Enable GT use, Switch G&C TLM to nominal after 1.5 hous | SECCHI Ops Lead email, 7/18/06 SECCHI GT Lead email, 8/29/06
RF | Step HGARA – BEHIND only | -- | 356 | 5 min | 720 | 241 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
SECCHI | Fully open EUVI, COR1, & COR2 doors. - BEHIND only | -- | 356 | 20 min | 720 | 241 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
3.2/3.2/3.6/2.2/0.6/3.3
***** | Saturday
S/C | S1+ Backup Delta V Maneuver- BEHIND only | -- | 357 | 4 hrs | 96 | 234 | Non-deterministic. Only if prime maneuver was not successful. | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
PLASTIC | Recover from S1+ Maneuver – BEHIND only | -- | 357 | 3 hrs | 720 | 241 |  | Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
***** | Sunday
PLASTIC | Recover from S1+ Maneuver – BEHIND only | -- | 358 | 3 hrs | 720 | 241 |  | Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
***** | Week 52 – BEHIND only
RF | Step HGARA – BEHIND only | -- | 360 | 5 min | 720 | 241 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
***** | Saturday
RF | Step HGARA – BEHIND only | -- | 364 | 5 min | 720 | 241 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
***** | Week 1 – BEHIND only
PWR G&C | Peak Power Test – BEHIND only | -- | 2 | 6 hrs | 720 | 241 | To characterize the PPT and power subsystem performance. Offpoints the S/C by 45 degree toward celestial south for 30 minutes. | PWR Lead Email 8/19/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ppt_test.prc
RF | Step HGARA – BEHIND only | -- | 3 | 5 min | 720 | 241 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
IMPACT G&C | IMPACT STE Sunglint Offpoint (UT event) | NA | 5 | 45 min | NA | NA | Before S2. Only on BEHIND to detemine sunglint on STE-U. Offpoint raster scan of + and - 2 deg in Y and Z axes in 1 deg steps with 1 minute dwells. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. | Weekly Planning mtg, 11/21/06
RF | Step HGARA – BEHIND only | -- | 7 | 5 min | 720 | 241 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
***** | Week 2 – BEHIND only
***** | AOS Next DSN Track
G&C | Disable GT Use – BEHIND only | -- | 8 | 2 min | 720 | 241 | Script: ahead_secchi_gt_pointing_disable.prc | G&C phone call 8/5/05
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Close COR1, COR2, & EUVI doors – BEHIND only | -- | 8 | 20 min | 720 | 241 |  | System Eng Lead email, 5/15/03
3.2/3.2/3.6/2.2/0.6/3.3
***** | AOS DSN Track – Maneuver
C&DH | Change to RTDFD 234 - 96 kbps - Delta V maneuvers, S/C & Instruments | -- | 8 | 2 min | 96 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/26.1
S/C | A5 Prime Delta V Maneuver- BEHIND only | -- | 8 | 4 hrs | 96 | 234 | 1900Z. Non-deterministic | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Change to RTDFD 241 - 720 kbps - S/C, Nominal Instruments | -- | 8 | 2 min | 720 | 241 | Macro 216. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Start SSR Playback | -- | 8 | 2 min | 720 | 241 | Starts SSR playback w/ single cmd | Mission Sim #4, 6/23/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ssr_playback_enable.prc
***** | AOS DSN Track – Post Maneuver
G&C | Enable GT Use – BEHIND only | -- | 8 | 2 min | 720 | 241 | Collect G&C GT performance data | G&C phone call 8/8/05
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: ahead_secchi_gt_pointing_enable.prc
PLASTIC | Recover from A5 Maneuver (1 of 2) – BEHIND only | -- | 8 | 3 hrs | 720 | 241 |  | Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Fully open EUVI, COR1, & COR2 doors. - BEHIND only | -- | 9 | 20 min | 720 | 241 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Change to RTDFD 246 - 720 kbps - Days 58 & others – BEHIND only | -- | 9 | 2 min | 720 | 246 | Macro 246. | MOps Script Rev, 8/3/06
3.2/3.2/93/2.2/0.6/3.3
SECCHI | Open HI Baffle Cover Door | -- | 9 | 15 min | 720 | 246 | Enable rule 70 (HI wax actuator protection) before starting. 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
| (Spacecraft-Commanded) – BEHIND only |  |  |  | 3.2/3.2/93/2/0/3.3 |  | Dependent on all maneuvers being completed
Script: secchi_hi_cover_deploy.prc
SECCHI | HI-1 and HI-2 First Light – BEHIND only | -- | 9 |  | 720 | 246 | 24 hrs after maneuver has completed | Early Ops Rev, 5/31/06
|  |  |  | 2 hrs | 3.2/3.2/93/2/0/3.3 |  | Dependent on all maneuvers being completed
C&DH | Change to RTDFD 241 - 720 kbps - S/C, Nominal Instruments – BEHIND only | -- | 9 | 2 min | 720 | 241 | Macro 241. | MOps Script Rev, 8/3/06
3.2/3.2/3.6/2.2/0.6/3.3
PLASTIC | Recover from A5 Maneuver (2 of 2) – BEHIND only | -- | 9 | 3 hrs | 720 | 241 |  | Ops WGM 4/21/04
3.2/3.2/3.6/2.2/0.6/3.3
S/C | A5 Backup Delta V Maneuver- BEHIND only | -- | 11 | 4 hrs | 96 | 234 | 1900Z. Non-deterministic. Only if prime maneuver was not successful. | Mission Design, 7/11/2005
3.2/3.2/3.6/2.2/0.6/26.1
Post A5
IMPACT | Deploy SIT and SEPT covers – BEHIND only | -- | 11 | 3 hrs | 720 | 241 | SEPT-NS and SEPT-E each have two covers. | IMPACT Lead email 4/29/03. TLM and SSR usage per lead worksheet 2-17-2004
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: impact_sept_cover_deploy.prc
IMPACT | SEPT Instruments commissioning BEHIND only | -- | 11 | 3 hrs | 720 | 241 | Post A5 | IMPACT Lead email 1/9/0. TLM and SSR usage per lead worksheet 2-17-20044
3.2/3.2/3.6/2.2/0.6/3.3
RF | Step HGARA – BEHIND only | -- | 11 | 5 min | 720 | 241 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days. | Mission Sim #1 Test Plan Rev, 12/20/04.
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
***** | Sunday
SWAVES | 1st SWAVES Smooth Calibration Rolls (UT event) - AHEAD only | 352 | -- | 10 hrs | NA | NA | Timetagged event (UT). Execute when system momentum is low, between 640,000 & 900,000 km, & to end 30 minutes before BOT due to G&C blackbox limitations. | SSC Lead email, 6/21/06
RF | HGA Checkout and Calibration #1 | 354 | 12 | 2 hrs |  | 241 | For BEHIND, need 20 kW uplink power from DSS for this track only | RF email, 3/4/04. DAO email 8/3/05.
For BEHIND, cross polarization in effect at DSS due to high downlink signal from HGA. Track starts at 3 kbps downlink and 1000 bps uplink (SOE L).
Desire GT on
[5 empty] | 720 |  | SPE angle = 144 deg (AHEAD).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | SPE angle = 166 deg (BEHIND)
Disable autonomy rule 25 (Monitor HGA health) before each test.
Earth range > 175,000 km
Script: hga_calibration.prc
SECCHI G&C | SECCHI HI Stray Light Calibration Offpoint (UT event) | -- | 13 | 1.5 hrs | NA | NA | Before June 15th. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. | SECCHI Ops Lead email, 10/3/06
RF | Switch downlink rate to 480 kbps downlink rate – BEHIND only | -- | 13 | 2 min | 480 | 239 | Macro 215, NRZ-L.
3.2/3.2/3.6/2.2/0.6/3.3
G&C | Change G&C TLM Schedule to collect GT & IMU high rate data – BEHIND only | -- | 13 to 17 | 10 min | 480 | 239 | APIDs 10C @ 7/sec & 12D @ 3/sec in RT. Schedule each day 5 minutes after the start of the instrument SSR PB if downlink rate is NOT 720 kbps | G&C Lead email, 12/14/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: gnc_gt_imu_tlm.prc
MOC | Switch DSN Data Download to retrieve from SPS | -- | 17 | NA | NA | NA | Was using NSS | JPL email, 1/7/07
RF | Switch downlink rate to 720 kbps downlink rate – BEHIND only | -- | 17 | 2 min | 720 | 241 | Macro 216, NRZ-L.
3.2/3.2/3.6/2.2/0.6/3.3
SWAVES | 2nd SWAVES Smooth Calibration Rolls (UT event) - AHEAD only | 354 | -- | 10 hrs | NA | NA | Timetagged event (UT). Execute when system momentum is low, between 640,000 & 900,000 km, & to end 30 minutes before BOT due to G&C blackbox limitations. | SSC Lead email, 6/21/06
***** | Week 3 – BEHIND only
RF | HGA Checkout and Calibration #2 | 355 | 18 | 2 hrs |  | 241 | For BEHIND, need 20 kW uplink power from DSS for this track only | RF email, 3/4/04. DAO email 8/3/05.
For BEHIND, cross polarization in effect at DSS due to high downlink signal from HGA. Track starts at 6 kbps downlink and 2000 bps uplink (SOE K).
Desire GT on
[5 empty] | 720 |  | SPE angle = 147 deg (AHEAD).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | SPE angle = 168 deg (BEHIND)
Disable autonomy rule 25 (Monitor HGA health) before each test.
Earth range > 175,000 km
Script: hga_calibration.prc
SWAVES | 3rd SWAVES Smooth Calibration Rolls (UT event) - AHEAD only | 357 | -- | 10 hrs | NA | NA | Timetagged event (UT). Execute when system momentum is low, between 640,000 & 900,000 km, & to end 30 minutes before BOT due to G&C blackbox limitations. | SSC Lead email, 6/21/06
C&DH | Change to RTDFD 234 - Delta V maneuvers, S/C & Instruments, 3.2/3.2/3.6/2.2/0.6/26.1– BEHIND only | -- | 21 | 2 min | 720 | 234 | Macro 234. Downlink in RT G&C maneuver TLM. Set PB ratio to 17 | G&C Lead email, 5/19/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Script: rtdfd14_pb17.prc
S/C | S2 – Second Lunar Swingby - BEHIND only | -- | 21 | 4 hrs | 720 | 234 | DV = 200 m/sec | Mission Design, 8/8/2006
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | BEHIND Altitude = 23,968 km
RF | Switch to 720 kbps downlink rate – BEHIND only | -- | 22 | 2 min | 720 | 241 | Macro 216.
3.2/3.2/3.6/2.2/0.6/3.3
| START OF STEREO PRIME SCIENCE MISSION – BEHIND only | -- | 22
S/C | Start Space Weather broadcast post-track – BEHIND only | -- | 22 | 2 min | 0/0/0/0/0.6/0 | 225 | Macro 205. Configure for space weather data rate, 633 bps, conv r=1/6 for non-DSN time. Since the space weather on the HGA exceeds PFD limits until day 104 for the Ahead S/C and until day 127 for the Behind S/C, it may be stopped within a day upon request from another country if interference to that country’s systems is detected. Pc/NO will decrease by 9 dB-Hz for space weather data rate. | RF Lead emails, 9/12/03 and 8/28/04
***** | Switch from 3 hour track DSN coverage to 4 hour tracks centered every 24 hours – | NA | 22
BEHIND only
C&DH/EA | Change XPNDR ranging modulation index to heliocentric orbit setting (0.305 rads) – BEHIND only | -- | 22 | 5 min | 720 | 241 | Increase ranging bandwidth for heliocentric orbit. Change macro 403 in EEPROM | RF Lead, 9/28/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: Load macro 403 from updated object rel.
C&DH/EA | Switch to using No Blackbox for S/C HSKP playback macros | -- | 22 | 5 min | 720 | 241 | Macro 434 for 720 kbps. (saves 177 Mbits) | RF Lead, 9/28/04
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Operational Mode – BEHIND only | -- | 22 |  | 720 | 241
SECCHI G&C | 3rd GT Calibration (UT event) - AHEAD only | 360 | -- | 1.5 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Configure G&C Blackbox for APIDs: 14F (Standby pkt) @ 1/second, 14C (GT Raw Messages @ 250 Hz) @ 7/second, 152 (RTW Output of Y and Z sung’s) @ 2/second, Enable GT use, Switch G&C TLM to nominal after 1.5 hous | SECCHI Ops Lead email, 7/18/06 SECCHI GT Lead email, 8/29/06
RF | Step HGARA – AHEAD only | 360 | -- | 5 min | 720 | 241 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
SECCHI G&C | 4th GT Calibration (UT event) | 362 | 25 | 1.5 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Configure G&C Blackbox for APIDs: 14F (Standby pkt) @ 1/second, 14C (GT Raw Messages @ 250 Hz) @ 7/second, 152 (RTW Output of Y and Z sung’s) @ 2/second, Enable GT use, Switch G&C TLM to nominal after 1.5 hous | SECCHI Ops Lead email, 7/18/06 SECCHI GT Lead email, 8/29/06
SWAVES | 2nd SWAVES Smooth Calibration Rolls (UT event) - BEHIND only | -- | 29 | 10 hrs | NA | NA | Timetagged event (UT). Execute when system momentum is low, between 640,000 & 900,000 km, & to end 30 minutes before BOT due to G&C blackbox limitations. | SSC Lead email, 6/21/06
SWAVES | 3rd SWAVES Smooth Calibration Rolls (UT event) - BEHIND only | -- | 31 | 10 hrs | NA | NA | Timetagged event (UT). Execute when system momentum is low, between 640,000 & 900,000 km, & to end 30 minutes before BOT due to G&C blackbox limitations. | SSC Lead email, 6/21/06
DSN | Begin using 20 KW uplink power for each track | -- | 31 | -- | -- | -- | Using 200 W uplink power from launch. If updated SOEs are not available, use pre-pass brief to advise of 20 KW uplink power. | RF Lead email, 6/9/06
RF | Switch to HGA and 720 kbps downlink rate | -- | 31 | 2 min | 720 | 241 | Macro 216, NRZ-L. Still on 200W uplink. For LGA use (momentum dump or autonoomy firing) before March 7th (20 kW uplink), need to lower uplink rate to 125 bps.
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Enable Rule 25 (Monitor HGA health when HGA is operated) | -- | 31 | 2 min | 720 | 241 | Be prepared for emergency data rate acquisition at the next DSN track | Fault Prot. mtg, 10/6/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: enable_rule_25.prc
Scheduler | Enable HGA Auto Track in all instrument events | -- | 31 | NA | NA | NA | IMPACT MAG Smooth, SECCHI EUVI Flat Field Offpoint, SECCHI GT cal, SECCHI HI Flat Field Roll, SECCHI Stepped Cal. Roll
DSN & Scheduler | Change SOE C & Q (360 kbps NRZ-L) to use HGA. | -- | 31 | NA | NA | NA | Launched with SOEs C & Q using LGA for phasing orbits. | SOE development, 2/3/06
RF | Switch downlink rate to 480 kbps downlink rate – AHEAD only | 363 | -- | 2 min | 480 | 239 | Macro 215, NRZ-L.
3.2/3.2/3.6/2.2/0.6/3.3
RF | Step HGARA – AHEAD only | 364 | -- | 5 min | 720 | 241 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
***** | Week 1 – AHEAD only
G&C | Change G&C TLM Schedule to collect GT & IMU high rate data – AHEAD only | 1 to 7 | -- | 10 min | 480 | 239 | APIDs 10C @ 7/sec & 12D @ 3/sec in RT. Schedule each day 5 minutes after the start of the instrument SSR PB if downlink rate is NOT 720 kbps | G&C Lead email, 12/14/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: gnc_gt_imu_tlm.prc
RF | Step HGARA – AHEAD only | 3 | -- | 5 min | 720 | 241 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
SECCHI G&C | SECCHI Driven EUVI Flat Field Calibration (UT event) | 4 | 35 | 1.5 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. For the S/C & MOps, this is a SECCHI GT Calibration event (use template: ahead_secchi_gt_cal.sch). Configure G&C Blackbox for APIDs: 14F (Standby pkt) @ 1/second, 14C (GT Raw Messages @ 250 Hz) @ 7/second, 152 (RTW Output of Y and Z sung’s) @ 2/second, Enable GT use, Switch G&C TLM to nominal after 1.5 hous | SECCHI Ops Lead email, 7/18/06, 10/13/06, SECCHI GT Lead email, 8/29/06
SECCHI | EUVI Flat Field Offpoint (UT event) | 5 | 36 | 6 hrs |  | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. S/C driven offpoints up to ±12 arc minutes in Y & Z axes. | SECCHI Ops lead email, 7/28/06
NA
RF | Switch downlink rate to 360 kbps downlink rate – AHEAD only | 6 | -- | 2 min | 360 | 237 | Macro 214, NRZ-L.
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Perform Stepped Calibration Roll (UT event) | 6 | 37 | 2 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04
G&C
PLASTIC
RF | Step HGARA – AHEAD only | 7 | -- | 5 min | 720 | 241 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
***** | Week 2 – AHEAD only
DSN | Begin using 20 KW uplink power for each track | 8 | -- | -- | -- | -- | Using 200 W uplink power from launch. If updated SOEs are not available, use pre-pass brief to advise of 20 KW uplink power. | RF Lead email, 6/9/06
RF | Switch to HGA and 720 kbps downlink rate | 8 | -- | 2 min | 720 | 241 | Macro 216, NRZ-L. Until Feb 21st (DOY 052), ensure that DSS is using reverse polarization (LCP) and 20kW uplink transmit power. For LGA use (momentum dump or autonoomy firing) before March 7th (20 kW uplink), need to lower uplink rate to 125 bps.
3.2/3.2/3.6/2.2/0.6/3.3
C&DH | Enable Rule 25 (Monitor HGA health when HGA is operated) | 8 | -- | 2 min | 720 | 241 | Be prepared for emergency data rate acquisition at the next DSN track | Fault Prot. mtg, 10/6/06
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: enable_rule_25.prc
Scheduler | Enable HGA Auto Track in all instrument events | 8 | -- | NA | NA | NA | IMPACT MAG Smooth, SECCHI EUVI Flat Field Offpoint, SECCHI GT cal, SECCHI HI Flat Field Roll, SECCHI Stepped Cal. Roll
DSN & Scheduler | Change SOE C & Q (360 kbps NRZ-L) to use HGA. | 8 | -- | NA | NA | NA | Launched with SOEs C & Q using LGA for phasing orbits. | SOE development, 2/3/06
SECCHI G&C | SECCHI HI Stray Light Calibration Offpoint (UT event) | 10 | -- | 1.5 hrs | NA | NA | Before June 15th. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. | SECCHI Ops Lead email, 10/3/06
RF | Step HGARA – AHEAD only | 11 | -- | 5 min | 720 | 241 | Move HGA similar to heliocentric orbit, i.e., 14 steps every 4 days | Mission Sim #1 Test Plan Rev, 12/20/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: hgara_step.prc
MOC | Switch DSN Data Download to retrieve from SPS | 16 | -- | NA | NA | NA | Was using NSS | JPL email, 1/7/07
***** | Week 3 – AHEAD only
C&DH | Operational Mode – AHEAD only | 18 | -- |  | 720 | 241
***** | Week 4 – AHEAD only
| START OF STEREO PRIME SCIENCE MISSION – AHEAD only | 22 | -- |  | 720 | 241
3.2/3.2/3.6/2.2/0.6/3.3
S/C | Start Space Weather broadcast post-track – AHEAD only | 22 | -- | 20.5 hrs | 0/0/0/0/0.6/0 | 225 | Macro 205. Configure for space weather data rate, 633 bps, conv r=1/6 for non-DSN time. Since the space weather on the HGA exceeds PFD limits until day 104 for the Ahead S/C and until day 127 for the Behind S/C, it may be stopped within a day upon request from another country if interference to that country’s systems is detected. Pc/NO will decrease by 9 dB-Hz for space weather data rate. | RF Lead emails, 9/12/03 and 8/28/04
C&DH/EA | Change XPNDR ranging modulation index to heliocentric orbit setting (0.305 rads) – AHEAD only | 22 | -- | 5 min | 720 | 241 | Increase ranging bandwidth for heliocentric orbit. Change macro 403 in EEPROM | RF Lead, 9/28/04
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Script: Load macro 403 from updated object rel.
C&DH/EA | Switch to using No Blackbox for S/C HSKP playback macros – AHEAD only | 22 | -- | 5 min | 720 | 241 | Macro 434 for 720 kbps. (saves 177 Mbits) | RF Lead, 9/28/04
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI | Lunar Transit of Solar Disk - BEHIND only | -- | 56 | 11 hrs | NA | NA | Feb 25th. 0656Z - edge of the Moon first touches the edge of the Sun, 0917Z - Moon's disk is first fully on the Sun's, 1658Z - advancing edge of the Moon again touches the Sun's edge, 1857Z - end of the transit. | Mission Design email, 12/20/06
RF | HGA Checkout and Calibration #3 – AHEAD only | 57 | -- | 2 hrs |  | 241 | Need DSN track | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 720 |  | SPE angle = 142 deg (AHEAD).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
MOC | Daylight Saving Time Begins | 70 | 70 | NA | NA | NA | Advance local time only one hour ahead. | Energy Policy Act of 2005
RF | HGA Checkout and Calibration #3 - BEHIND only | -- | 71 | 2 hrs |  | 241 | Need DSN track | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 720 |  | SPE angle = 17 deg BEHIND)
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
SECCHI G&C | SECCHI HI Coincident 90/270 Roll (UT event) | 72 | 72 | 2.5 hrs | NA | NA | Before March 15th. Schedule to occur simultaneously on both S/C. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. | SECCHI Ops Lead email, 10/3/06
SECCHI G&C | SECCHI HI 180 Roll (UT event) | 74 | 74 | 1.5 hrs | NA | NA | Before March 15th. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. | SECCHI Ops Lead email, 10/3/06
RF | HGA Checkout and Calibration #4 | 93 | 93 | 2 hrs |  | 241 | Need DSN track | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 720 |  | SPE angle = 130 deg (AHEAD). SPE angle = 34 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
C&DH | Update C&DH auto exec macro 0 to configure S/C at 10 kbps downlink and 2000 bps uplink rate and ranging off (macro 209) | 94 | 94 | 10 min |  |  | Launch 30 kbps downlink rate and 2000 bps uplink. Max. LGA rates: 10 kbps downlink, 2000 bps uplink. AHEAD = April 12, 2007, BEHIND = April 5, 2007 | RF Lead email, 12/19/06
SECCHI | SECCHI Stepped Calibration Roll (UT event) | -- | 107 | 3 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04
G&C
PLASTIC
SECCHI G&C | GT Offpoint Calibration (UT event) | 109 | 109 | 1.5 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Configure G&C Blackbox for APIDs: 14F (Standby pkt) @ 1/second, 14C (GT Raw Messages @ 250 Hz) @ 7/second, 152 (RTW Output of Y and Z sung’s) @ 2/second, Enable GT use, Switch G&C TLM to nominal after 1.5 hous | SECCHI Ops Lead email, 7/18/06 SECCHI GT Lead email, 8/29/06
MOC | Start Unattended Track Operations | 120 | 120 | NA | NA | NA | Real-time commanding available on Wednesdays | Unattended Track CONOPs Peer Rev., 4/12/07
SECCHI | 1st SECCHI Campaign | 124 to 137 | 124 to 137 | -- | -- | -- | Additional 3 hour track 12 hours after the start of the daily track | SECCHI Ops Lead email, 1/25/07
C&DH | Update C&DH auto exec macro 0 to configure S/C at 6 kbps downlink and 2000 bps uplink rate and ranging off (macro 208) | 136 | 136 | 10 min |  |  | Adjust rates for maximum S/C range. Max. LGA rates: 6 kbps downlink, 2000 bps uplink. AHEAD = May 24, 2007, BEHIND = May 18, 2007 | RF Lead email, 12/19/06
C&DH | Update C&DH auto exec macro 0 to configure S/C at 3 kbps downlink and 1000 bps uplink rate and ranging off (macro 207) | 157 | 157 | 10 min |  |  | Adjust rates for maximum S/C range. Max. LGA rates: 3 kbps downlink, 1000 bps uplink. AHEAD = June 18, 2007, BEHIND = June 9, 2007 | RF Lead email, 12/19/06
All | Minimum Mission Success | 172 | 172 | NA |  |  | Both S/C 150 days on heliocentric orbit. | Project Scientist FOR pres., 4/25/06
G&C | Test new macro 145 to use ST rates when IMUB is disabled | 178 | -- | 20 min | 720 | 241 | RT (RTDR from FP) test during a track. Fine pointing may drop in and out. | Systems request, 5/14/07
S/C | 6th Momentum Dump - AHEAD only | 186 | -- | 1.5 hrs | 720 | 234 | Thruster set A, on HGA
3.2/3.2/3.6/2.2/0.6/26.1
RF | HGA Checkout and Calibration #5 | 192 | 192 | 2 hrs |  | 241 | Need 7 hr DSN track | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 720 |  | SPE angle = 103 deg (AHEAD). SPE angle = 62 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
C&DH | Update C&DH auto exec macro 0 to configure S/C at 1 kbps downlink and 500 bps uplink rate and ranging off (macro 206) | 192 | 192 | 10 min |  |  | Adjust rates for maximum S/C range. Max. LGA rates: 1 kbps downlink, 500 bps uplink. AHEAD = July 31, 2007, BEHIND = July 13, 2007 | RF Lead email, 12/19/06
S/C | 4th Momentum Dump - BEHIND only | -- | 206 | 1.5 hrs | 720 | 234 | Thruster set A, on HGA
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 7th Momentum Dump - AHEAD only | 227 | -- | 1.5 hrs | 720 | 234 | Thruster set A, on HGA
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 8th & 5th Momentum Dumps - AHEAD & BEHIND | 269 | 269 | 1.5 hrs | 720 | 234 | Thruster set A, on HGA
3.2/3.2/3.6/2.2/0.6/26.1
RF | HGA Checkout and Calibration #6 | 276 | 276 | 2 hrs |  | 241 | Need 7 hr DSN track | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 720 |  | SPE angle = 88 deg (AHEAD). SPE angle = 70 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
MOC | Daylight Saving Time Ends | 308 | 308 | NA | NA | NA | Set local time only one hour back. | Energy Policy Act of 2005
S/C | 9th Momentum Dump - AHEAD only | 311 | -- | 1.5 hrs | 720 | 234 | Thruster set A, on HGA
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Update C&DH auto exec macro 0 to configure S/C at 633 bps downlink and 125 bps uplink rate and ranging off (macro 202) - BEHIND only | 318 | 318 | 10 min |  |  | Adjust rates for maximum S/C range. Max. LGA rates: 633 bps downlink, 125 bps uplink. AHEAD = March 29, 2008 BEHIND = November 15, 2007 | RF Lead email, 12/19/06
S/C | 6th Momentum Dump - BEHIND only | -- | 332 | 1.5 hrs | 720 | 234 | Thruster set A, on HGA
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 10th Momentum Dump - AHEAD only | 353 | -- | 1.5 hrs | 720 | 234 | Thruster set A, on HGA
3.2/3.2/3.6/2.2/0.6/26.1
***** | 2008
SECCHI G&C | 3rd SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 3 | -- | 3 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD aphelion on DOY 006 | SECCHI Ops Lead email, 11/30/07
SECCHI | 2nd SECCHI Campaign | 7 thru 20 | 7 thru 20 | -- | -- | -- | Additional 3 hour track 12 hours after the start of the daily track | SECCHI Ops Lead email, 7/2/07
S/C | 11th & 7th Momentum Dumps - AHEAD & BEHIND | 37 | 23 | 2 hrs | 720 | 234 | Thruster set A, on HGA
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 3rd SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 50 | 3 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND perihelion on DOY 047 | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04
MOC | Daylight Saving Time Begins | 69 | 69 | NA | NA | NA | Advance local time only one hour ahead. | Energy Policy Act of 2005
S/C | 8th Momentum Dump - BEHIND only | -- | 79 | 2 hrs | 720 | 234 | Thruster set A, on HGA. Every 63 days.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 12th Momentum Dump - AHEAD only | 86 | -- | 2 hrs | 720 | 234 | Thruster set A, on HGA. Every 42 days.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 4th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 92 | -- | 3 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations.Every aphelion, perihelion, and midpoints between aphelion and perihelion. | SECCHI Telecon 1/23/04. SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04
RF | HGA Checkout and Calibration #7 | 93 | 93 | 2 hrs |  | 241 | Need 8 hr DSN track | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 720 |  | SPE angle = 82 deg (AHEAD). SPE angle = 75 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
S/C | 13th Momentum Dump - AHEAD only | 128 | -- | 2 hrs | 720 | 234 | Thruster set A, on HGA. Every 42 days.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 9th Momentum Dump - BEHIND only | -- | 135 | 2 hrs | 720 | 234 | Thruster set A, on HGA. Every 63 days.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 4th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 141 | 3 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 144. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
C&DH | Update C&DH auto exec macro 0 to configure S/C at 35 bps downlink and 125 bps uplink rate and ranging off (macro 201) | 156 | 156 | 10 min |  |  | Adjust rates for maximum S/C range. Max. LGA rates: 35 bps downlink, 125 bps uplink. AHEAD = June 12, 2008, BEHIND = July 4, 2008 | RF Lead email, 2/15/08
S/C | 14th Momentum Dump - AHEAD only | 170 | -- | 2 hrs | 720 | 234 | Thruster set A, on HGA. Every 42 days.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 5th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 176 | -- | 3 hrs | NA | NA | Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD perihelion on DOY 179:23:55Z | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
RF | HGA Checkout and Calibration #8 | 191 | 191 | 2 hrs |  | 233 | Need 8 hr DSN track | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 96 |  | SPE angle = 79 deg (AHEAD). SPE angle = 67 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
S/C | 10th Momentum Dump - BEHIND only | -- | 198 | 2 hrs | 720 | 234 | Thruster set A, on HGA. Every 63 days.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 15th Momentum Dump - AHEAD only | 212 | -- | 2 hrs | 720 | 234 | Thruster set A, on HGA. Every 42 days.
3.2/3.2/3.6/2.2/0.6/26.1
DSN | Begin 5 hour daily DSN tracks | 217 | 217 | NA | 720 | 234 | Begin on Aug 4th. May need to switch to 480 kbps due to low SSNR - track dependent | ULP, rev 071129
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI G&C | 6th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 239 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND aphelion on DOY 241:20:00Z. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
RF | Switch downlink rate to 480 kbps downlink rate- BEHIND only | -- | 259 | 2 min | 480 | 239 | Macro 215, NRZ-L. BEHIND = Sep 15, 2008, Assumes 34 m subnet at 1.5 dB link margin. | RF Lead email, 7/22/08
3.2/3.2/3.6/2.2/0.6/3.3
S/C | 16th Momentum Dump - AHEAD only | 260 | -- | 2 hrs | 720 | 234 | Thruster set A, on HGA. Every 42 days.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 11th Momentum Dump - BEHIND only | -- | 268 | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 63 days.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 6th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 274 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 264. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
RF | Switch downlink rate to 480 kbps downlink rate- AHEAD only | 287 | -- | 2 min | 480 | 239 | Macro 215, NRZ-L. AHEAD = Oct 13, 2008, Assumes 34 m subnet at 1.5 dB link margin. | RF Lead email, 7/22/08
3.2/3.2/3.6/2.2/0.6/3.3
S/C | 17th Momentum Dump - AHEAD only | 303 | -- | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days.
3.2/3.2/3.6/2.2/0.6/26.1
MOC | Daylight Saving Time Ends | 307 | 307 | NA | NA | NA | First Sunday in November. Set local time only one hour back. | Energy Policy Act of 2005
S/C | 12th Momentum Dump - BEHIND only | -- | 331 | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 63 days.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 7th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 337 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD aphelion on DOY 350:05:43Z | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
C&DH | Update macro 201 to configure S/C at 35 bps downlink and 7.8125 bps uplink rate and ranging off | -- | 338 | 30 min |  |  | Adjust rates for maximum S/C range. Max. LGA rates: 35 bps downlink, 7.8125 bps uplink. AHEAD = April 23, 2009, BEHIND = Dec 11, 2008 | RF Lead email, 2/15/08
SECCHI G&C | 7th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 351 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 338. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 18th Momentum Dump - AHEAD only | 352 | -- | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days.
3.2/3.2/3.6/2.2/0.6/26.1
***** | 2009
RF | HGA Checkout and Calibration #9 | 7 | 7 | 2 hrs |  | 233 | Need 8 hr DSN track | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 96 |  | SPE angle = 69 deg (AHEAD). SPE angle = 64 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
S/C | 13th Momentum Dump - BEHIND only | -- | 21 | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 63 days.
3.2/3.2/3.6/2.2/0.6/26.1
| End of Prime Science Mission (EOPM) | 22 | 22 | NA | NA | NA
| Start of Extended Mission #1 | 22 | 22 | NA | NA | NA
S/C | 19th Momentum Dump - AHEAD only | 35 | -- | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days.
3.2/3.2/3.6/2.2/0.6/26.1
MOC | Begin using CCSDS SLE TLM service | 54 | 54 | NA | NA | NA | VC7 data using TCP/IP protocol on IONet. No change to off-line data delivery. | DMR
S/C | IMU2 Checkout - BEHIND only | -- | 55 | 4 hrs | 480 | 239 | Characterize IMU2 performance. IMU1 off.
3.2/3.2/3.6/2.2/0.6/26.1
MOC | Daylight Saving Time Begins | 67 | 67 | NA | NA | NA | Second Sunday in March. Advance local time only one hour ahead. | Energy Policy Act of 2005
SECCHI G&C | 8th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 69 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 69. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 14th Momentum Dump - BEHIND only | -- | 70 | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 1st SECCHI HI 180 Roll (UT event) | 71 | 77 | 6.6 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set start time to 10 minutes before an even numbered hour. Set to end 30 minutes before BOT due to G&C blackbox limitations. Every 4 weeks. To view L4/L5 point. | SECCHI Ops Lead email 2/9/09.
S/C | 20th Momentum Dump - AHEAD only | 84 | -- | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 9th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 97 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND perihelion on DOY 070:15:28Z. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
SECCHI G&C | 2nd SECCHI HI 180 Roll (UT event) | 98 | 98 | 6.6 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set start time to 10 minutes before an even numbered hour. Set to end 30 minutes before BOT due to G&C blackbox limitations. Every 4 weeks. To view L4/L5 point. | SECCHI Ops Lead email 2/9/09.
S/C | Switch to IMU1 - BEHIND only | -- | 98 | 4 hrs | 480 | 239 | IMU2 off. On for 41 days.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 15th Momentum Dump - BEHIND only | -- | 112 | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 3rd SECCHI HI 180 Roll (UT event) | 119 | 126 | 6.6 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set start time to 10 minutes before an even numbered hour. Set to end 30 minutes before BOT due to G&C blackbox limitations. Every 4 weeks. To view L4/L5 point. | SECCHI Ops Lead email 2/9/09.
S/C | 21st Momentum Dump - AHEAD only | 132 | -- | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | System Reset to EA mode to jump to G&C 3.2.6 - BEHIND only | -- | 132 | 8 hrs | 633 bps | 284 | 70m - 633/125 bps, 34m - 35/7.8125 bps data rates. Schedule when system momentum is low. | If approved by GSFC.
[5 empty] | 0/0/0/0/0/0.035 |  | Will power off all instruments and ST
Ensure UTCF and S/C ephemeris in EE is the latest. S/C rolls clockwise when viewed along +X (looking at the Sun). Will lose all stored timetag commands. Plan to reload UT events after recovery.
Script: EA_recovery.prc
SECCHI G&C | 4th SECCHI HI 180 Roll (UT event) | 147 | 147 | 6.6 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set start time to 10 minutes before an even numbered hour. Set to end 30 minutes before BOT due to G&C blackbox limitations. Every 4 weeks. To view L4/L5 point. | SECCHI Ops Lead email 2/9/09.
S/C | 16th Momentum Dump - BEHIND only | -- | 154 | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 9th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 160 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD perihelion on DOY 158:18:45Z | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
SECCHI G&C | 10th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 167 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 167. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
SECCHI G&C | 5th SECCHI HI 180 Roll (UT event) | 168 | 168 | 6.6 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set start time to 10 minutes before an even numbered hour. Set to end 30 minutes before BOT due to G&C blackbox limitations. Every 4 weeks. To view L4/L5 point. | SECCHI Ops Lead email 2/9/09.
S/C | 22nd Momentum Dump - AHEAD only | 175 | -- | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
RF | HGA Checkout and Calibration #10 | 183 | 182 | 2 hrs prep, 1 hr execute |  | 233 | Need 8 hr DSN track | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 96 |  | SPE angle = 66 deg (AHEAD). SPE angle = 61 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/3.3 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
SECCHI G&C | 6th SECCHI HI 180 Roll (UT event) | 189 | 189 | 6.6 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set start time to 10 minutes before an even numbered hour. Set to end 30 minutes before BOT due to G&C blackbox limitations. Every 4 weeks. To view L4/L5 point. | SECCHI Ops Lead email 2/9/09.
S/C | 17th Momentum Dump - BEHIND only | -- | 204 | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 23rd Momentum Dump - AHEAD only - to set system momentum low for G&C 3.2.6 FSW activation/system reset | 209 | -- | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 7th SECCHI HI 180 Roll (UT event) | 211 | 217 | 6.6 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set start time to 10 minutes before an even numbered hour. Set to end 30 minutes before BOT due to G&C blackbox limitations. Every 4 weeks. To view L4/L5 point. | SECCHI Ops Lead email 2/9/09.
S/C | System Reset to EA mode to jump to G&C 3.2.6 - AHEAD only | 216 | -- | 8 hrs | 633 bps | 284 | 70m - 633/125 bps, 34m - 35/7.8125 bps data rates. Schedule when system momentum is low. | Approved by GSFC on 5/5/09.
[5 empty] | 0/0/0/0/0/0.035 |  | Will power off all instruments and ST
Ensure UTCF and S/C & Earth ephemerides in EE are the latest. S/C rolls clockwise when viewed along +X (looking at the Sun). Will lose all stored timetag commands. Plan to reload UT events after recovery.
Script: EA_recovery.prc
DSN | Begin 6 hour daily DSN tracks | 222 | 222 | NA | 480 | 239 | Begin on Aug 10, 2009. | ULP, rev 081106
3.2/3.2/3.6/2.2/0.6/3.3
SECCHI G&C | 8th SECCHI HI 180 Roll (UT event) | 225 | -- | 6.6 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set start time to 10 minutes before an even numbered hour. Set to end 30 minutes before BOT due to G&C blackbox limitations. Every 4 weeks. To view L4/L5 point. | SECCHI Ops Lead email 2/9/09.
RF | Switch downlink rate to 360 kbps downlink rate | 229 | 251 | 2 min | 360 | 237 | Macro 214, NRZ-L. Need by AHEAD = Aug 26, 2009, BEHIND = Sep 15, 2009, Assumes 34 m subnet. RF margin 2 dB. | RF Lead email, 3/5/09
3.2/3.2/3.6/2.2/0.6/3.3
S/C | 24th Momentum Dump - AHEAD only | 238 | -- | 2 hrs | 360 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 10th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 253 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 243. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
| AHEAD Observatory at L4 Libration Point | 255 | -- | NA | NA | NA | Sep. 12, 2009. 60 deg Earth-Sun-Probe angle. | Mission Design email, 5/19/08
S/C | 18th Momentum Dump - BEHIND only | -- | 259 | 2 hrs | 480 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 11th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 272 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 30 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND aphelion on DOY 264:20:44Z. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 25th Momentum Dump - AHEAD only | 287 | -- | 2 hrs | 360 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
| BEHIND Observatory at L5 Libration Point | -- | 299 | NA | NA | NA | Oct 26, 2009. 60 deg Earth-Sun-Probe angle. | Mission Design email, 5/19/08
G&C | Refresh IMU EEPROM | 299 | 299 | 30 min | 360 | ??? | Every 3 years | IMU manufacturer spec.
0.11/0.56/2.2/0.07/0.6/1
MOC | Daylight Saving Time Ends | 305 | 305 | NA | NA | NA | First Sunday in November. Set local time only one hour back. | Energy Policy Act of 2005
S/C | 19th Momentum Dump - BEHIND only | -- | 308 | 2 hrs | 360 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 11th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 328 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD aphelion on DOY 329:05:38Z | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 26th Momentum Dump - AHEAD only | 337 | -- | 2 hrs | 360 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
DSN | Begin 7 hour daily DSN tracks - BEHIND only | -- | 334 | NA | 360 | 237 | Begin on BEHIND only on Nov 30, 2009. | ULP, rev 081106
3.2/3.2/3.6/2.2/0.6/3.3
RF | Switch downlink rate to 240 kbps downlink rate - BEHIND only | -- | 341 | 2 min | 240 | ??? | Macro ???, Bi-phase L. Need by AHEAD =May 3, 2010, BEHIND = Dec 14, 2009, Assumes 34 m subnet. RF margin 2 dB. | RF Lead email, 3/5/09
0.11/0.56/2.2/0.07/0.6/1
C&DH | Update C&DH auto exec macro 0 to configure S/C at 11 bps downlink and 7.8125 bps uplink rate and ranging off (macro 200) – BEHIND only | -- | 343 | 30 min |  |  | Adjust rates for maximum S/C range. Max. LGA rates: 11 bps downlink, 7.8125 bps uplink. BEHIND = Dec 16, 2009 | RF Lead email, 2/15/08
S/C | 20th Momentum Dump - BEHIND only | -- | 357 | 2 hrs | 360 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
***** | 2010
SECCHI G&C | 12th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 5 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 361. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
RF | HGA Checkout and Calibration #11 | 6 | 6 | 2 hrs prep, 1 hr execute |  | 234 |  | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 96 |  | SPE angle = 58 deg (AHEAD). SPE angle = 52 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: xxxxx_hga_half_deg_calibration.sch
S/C | 27th Momentum Dump - AHEAD only | 19 | -- | 2 hrs | 360 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 21st Momentum Dump - BEHIND only | -- | 37 | 2 hrs | 240 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 12th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 54 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 51. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 28th Momentum Dump - AHEAD only | 67 | -- | 2 hrs | 360 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
MOC | Daylight Saving Time Begins | 73 | 73 | NA | NA | NA | Second Sunday in March. Advance local time only one hour ahead. | Energy Policy Act of 2005
S/C | 22nd Momentum Dump - BEHIND only | -- | 77 | 2 hrs | 240 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 13th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 96 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND perihelion on DOY 094:17:59Z. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | Load G&C 3.2.6 FSW to Copy 1 EEPROM | 105 | 98 | 3 hrs | 360 | 234 | Previously loaded to EEPROM copy 2 on AHEAD DOY 211 in support of FSW activation on DOY 216 and on BEHIND DOY 127 in support of FSW activation on DOY 132. | Approved by GSFC on 5/5/09.
3.2/3.2/3.6/2.2/0.6/26.1
DSN | Begin 7 hour daily DSN tracks - AHEAD only | 109 | -- | NA | 360 | 237 | Begin on AHEAD only on Apr 19, 2010. | ULP, rev 081106
3.2/3.2/3.6/2.2/0.6/3.3
S/C | 29th Momentum Dump - AHEAD only | 111 | -- | 2 hrs | 360 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
RF | Switch downlink rate to 240 kbps downlink rate – AHEAD only | 116 | -- | 2 min | 240 | 236 | Macro 217, NRZ-L. Need by AHEAD =May 3, 2010, BEHIND = Dec 14, 2009, Assumes 34 m subnet. RF margin 2 dB. | RF Lead email, 3/5/09
0.1/1.18/2.2/0.07/0.6/2.7
S/C | 23rd Momentum Dump - BEHIND only | -- | 117 | 2 hrs | 240 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
C&DH | Update C&DH auto exec macro 0 to configure S/C at 11 bps downlink and 7.8125 bps uplink rate and ranging off (macro 200) – AHEAD only | 132 | -- | 30 min |  |  | Adjust rates for maximum S/C range. Max. LGA rates: 11 bps downlink, 7.8125 bps uplink. AHEAD = May 23, 2010 | RF Lead email, 2/15/08
SECCHI G&C | 13th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 138 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD perihelion on DOY 138:18:57Z | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 30th Momentum Dump - AHEAD only | 158 | -- | 2 hrs | 240 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 24th Momentum Dump - BEHIND only | -- | 160 | 2 hrs | 240 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
RF | HGA Checkout and Calibration #12 | 195 | 182 | 1 hr prep, 1 hr execute |  | 234 |  | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 96 |  | SPE angle = 53 deg (AHEAD). SPE angle = 53 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: xxxxx_hga_half_deg_calibration.sch
SECCHI G&C | 14th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 194 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 191. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 31st Momentum Dump - AHEAD only | 202 | -- | 2 hrs | 240 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 25th Momentum Dump - BEHIND only | -- | 207 | 2 hrs | 240 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 14th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 222 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 223. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 32nd Momentum Dump - AHEAD only | 244 | -- | 2 hrs | 240 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 26th Momentum Dump - BEHIND only | -- | 252 | 2 hrs | 240 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
| End of Extended Mission #1 | 273 | 273 | NA | NA | NA | Ends at FY2010
SECCHI G&C | 15th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 285 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND aphelion on DOY 289 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 33rd Momentum Dump - AHEAD only | 290 | -- | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 27th Momentum Dump - BEHIND only | -- | 302 | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
MOC | Daylight Saving Time Ends | 311 | 311 | NA | NA | NA | First Sunday in November. Set local time only one hour back. | Energy Policy Act of 2005
SECCHI G&C | 15th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 313 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD aphelion on DOY 310 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 34th Momentum Dump - AHEAD only | 335 | -- | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 28th Momentum Dump - BEHIND only | -- | 351 | 2 hrs | 120 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
***** | 2011
RF | HGA Checkout and Calibration #13 | 12 | 12 | 2 hr prep, 1 hr execute |  | 234 |  | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 96 |  | SPE angle = 47 deg (AHEAD). SPE angle = 42 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: xxxxx_hga_half_deg_calibration.sch
S/C | 35th Momentum Dump - AHEAD only | 19 | -- | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 29th Momentum Dump - BEHIND only | -- | 30 | 2 hrs | 120 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 16th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 32 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 31. | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
SECCHI G&C | 16th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 39 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 21 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 36th Momentum Dump - AHEAD only | 65 | -- | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 30th Momentum Dump - BEHIND only | -- | 70 | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
MOC | Daylight Saving Time Begins | 72 | 72 | NA | NA | NA | Second Sunday in March. Advance local time only one hour ahead. | Energy Policy Act of 2005
S/C | 31st Momentum Dump - BEHIND only | -- | 110 | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 37th Momentum Dump - AHEAD only | 113 | -- | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 17th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 116 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD perihelion on DOY 118 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
SECCHI G&C | 17th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 116 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND perihelion on DOY 119 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
DSN | Begin 8 hour daily DSN tracks | 150 | 150 | NA | NA | NA | Begin on May 30, 2011. | RF Lead email, 7/23/10
S/C | 32nd Momentum Dump - BEHIND only | -- | 150 | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 38th Momentum Dump - AHEAD only | 155 | -- | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
RF | Switch downlink rate to 160 kbps downlink rate - AHEAD | 178 | -- | NA | 160 | 235 | Macro 212, Bi-phase L. Need by June 27, 2011, Assumes 34 m subnet. RF margin 2 dB, 90% weather, & 10 deg elevation | RF Lead email, 7/23/10
0.1/1.18/2.2/0.07/0.6/2.7
RF | Begin use of 480 kbps downlink rate on 70 m DSN subnet - AHEAD | 178 | -- | NA | 480 | 239 | Macro 215, NRZ-L. AHEAD = June 27,, 2011, Assumes 70 m subnet | RF Lead email, 7/23/10
3.2/3.2/3.6/2.2/0.6/3.3
RF | Switch downlink rate to 160 kbps downlink rate- BEHIND | -- | 192 | NA | 160 | 235 | Macro 212, Bi-phase L. Need by July 15, 2011, Assumes 34 m subnet. RF margin 2 dB, 90% weather, & 10 deg elevation | RF Lead email, 7/23/10
0.1/1.18/2.2/0.07/0.6/2.7
RF | Begin use of 480 kbps downlink rate on 70 m DSN subnet -BEHIND | -- | 192 | NA | 480 | 239 | Macro 215, NRZ-L. BEHIND = July 15, 2011, Assumes 70 m subnet | RF Lead email, 7/23/10
3.2/3.2/3.6/2.2/0.6/3.3
S/C | 33rd Momentum Dump - BEHIND only | -- | 193 | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
RF | HGA Checkout and Calibration #14 | 194 | 194 | 2 hr prep, 1 hr execute |  | 234 |  | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 96 |  | SPE angle = 42 deg (AHEAD). SPE angle = 43 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: xxxxx_hga_half_deg_calibration.sch
S/C | 39th Momentum Dump - AHEAD only | 197 | -- | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 18th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 207 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 204 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
SECCHI G&C | 18th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 214 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 216 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 34th Momentum Dump - BEHIND only | -- | 237 | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 40th Momentum Dump - AHEAD only | 239 | -- | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 41st Momentum Dump - AHEAD only | 280 | -- | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 35th Momentum Dump - BEHIND only | -- | 283 | 2 hrs | 160 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 19th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 291 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD aphelion on DOY 290 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
MOC | Daylight Saving Time Ends | 310 | 310 | NA | NA | NA | First Sunday in November. Set local time only one hour back. | Energy Policy Act of 2005
PWR | 1st Battery Discharge Cycle - AHEAD only | 311 | -- | 2 hrs | 160 | 235 | Annually at aphelion. SSR playback will occur throughout. Backup with RT command to restore VT level to 13. | PWR Lead Email 10/12/11
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 19th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 312 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND aphelion on DOY 313 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 42nd Momentum Dump - AHEAD only | 321 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
PWR | 1st Battery Discharge Cycle - BEHIND only | -- | 322 | 2 hrs | 160 | 235 | Annually at aphelion. SSR playback will occur throughout. Backup with RT command to restore VT level to 13. | PWR Lead Email 10/12/11
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 36th Momentum Dump - BEHIND only | -- | 324 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
| End LGA Downlink on 34 m DSN subnet – BEHIND | -- | 336 | NA | NA | NA | 3 dB margin, ends Dec 2, 2011. Use 70m for emergency use. | RF Lead email, 7/23/10
S/C | 43rd Momentum Dump - AHEAD only | 363 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
***** | 2012
S/C | 37th Momentum Dump - BEHIND only | -- | 1 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 20th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 10 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 011 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
RF | HGA Checkout and Calibration #15 | 11 | 11 | 2 hr prep, 1 hr execute |  | 234 | Need HEMT receiver | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 96 |  | SPE angle = 36 deg (AHEAD). SPE angle = 32 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: xxxxx_hga_half_deg_calibration.sch
S/C | 38th Momentum Dump - BEHIND only | -- | 32 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 44th Momentum Dump - AHEAD only | 33 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 20th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 45 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 045 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
MOC | Daylight Saving Time Begins | 71 | 71 | NA | NA | NA | Second Sunday in March. Advance local time only one hour ahead. | Energy Policy Act of 2005
S/C | 45th Momentum Dump - AHEAD only | 65 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 39th Momentum Dump - BEHIND only | -- | 68 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 21st SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 94 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD perihelion on DOY 097 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 40th Momentum Dump - BEHIND only | -- | 102 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 46th Momentum Dump - AHEAD only | 107 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
| End LGA Downlink on 34 m DSN subnet – AHEAD | 121 | -- | NA | NA | NA | 3 dB margin, April 30, 2012. Use 70m for emergency use. | RF Lead email, 7/23/10
S/C | 41st Momentum Dump - BEHIND only | -- | 138 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 21st SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 143 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND perihelion on DOY 143 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 47th Momentum Dump - AHEAD only | 152 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 42nd Momentum Dump - BEHIND only | -- | 164 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 22nd SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 185 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 183 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 48th Momentum Dump - AHEAD only | 193 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
RF | HGA Checkout and Calibration #16 | 193 | 193 | 2 hr prep, 1 hr execute |  | 234 | Need HEMT receiver | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 96 |  | SPE angle = 30 deg (AHEAD). SPE angle = 32 deg (BEHIND).
[5 empty] | 3.2/3.2/3.6/2.2/0.6/26.1 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
S/C | 43rd Momentum Dump - BEHIND only | -- | 202 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 49th Momentum Dump - AHEAD only | 237 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 44th Momentum Dump - BEHIND only | -- | 238 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 22nd SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 241 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 240 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
SECCHI G&C | 23rd SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 269 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD aphelion on DOY 270 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
PWR | 2nd Battery Discharge Cycle - AHEAD only | 270 | -- | 2 hrs | 160 | 2335 | Annually at aphelion. SSR playback will occur throughout. Backup with RT command to restore VT level to 13. | PWR Lead Email 10/12/11
3.2/3.2/3.6/2.2/0.6/26.1
| End of Extended Mission #2 | 274 | 274 | NA | NA | NA | Ends at FY2012
S/C | 50th Momentum Dump - AHEAD only | 275 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 45th Momentum Dump - BEHIND only | -- | 276 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
| End LGA Uplink on 34 m DSN subnet – BEHIND | -- | 298 | NA | NA | NA | 6 dB margin, ends Oct 24, 2012 | RF Lead email, 7/23/10
G&C | Refresh IMU EEPROM | 299 | 299 | 30 min | 30 | ??? | Every 3 years | IMU manufacturer spec.
0.11/0.56/2.2/0.07/0.6/1
| End LGA Uplink on 34 m DSN subnet – AHEAD | 300 | -- | NA | NA | NA | 6 dB margin, ends Oct 26, 2012 | RF Lead email, 7/23/10
S/C | 51st Momentum Dump - AHEAD only | 309 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
MOC | Daylight Saving Time Ends | 309 | 309 | NA | NA | NA | First Sunday in November. Set local time only one hour back. | Energy Policy Act of 2005
RF | Switch downlink rate to 120 kbps downlink rate - BEHIND only | -- | 310 | NA | 120 | 231 | Macro 218, Bi-phase L. Need by BEHIND = Nov 5, 2012, Assumes 34 m subnet. RF margin 2 dB, 90% weather, & 10 deg elevation | RF Lead email, 9/6/11
0.1/1.18/2.2/0.07/0.6/2.7
S/C | 46th Momentum Dump - BEHIND only | -- | 312 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 23rd SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 339 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND aphelion on DOY 337 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
PWR | 2nd Battery Discharge Cycle - BEHIND only | -- | 340 | 2 hrs | 160 | 235 | Annually at aphelion. SSR playback will occur throughout. Backup with RT command to restore VT level to 13. | PWR Lead Email 10/12/11
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 52nd Momentum Dump - AHEAD only | 348 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 24th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 353 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 356 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 47th Momentum Dump - BEHIND only | -- | 355 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
***** | 2013
RF | HGA Checkout and Calibration #17 | 10 | 10 | 2 hr prep, 1 hr execute |  | 232 | Need HEMT receiver | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 30 |  | SPE angle = 25 deg (AHEAD). SPE angle = 22 deg (BEHIND).
[5 empty] | 3.2/1/1.8/2.2/0/9.4 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
S/C | 53rd Momentum Dump - AHEAD only | 15 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 48th Momentum Dump - BEHIND only | -- | 31 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 54th Momentum Dump - AHEAD only | 50 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 49th Momentum Dump - BEHIND only | -- | 50 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
MOC | Daylight Saving Time Begins | 69 | 69 | NA | NA | NA | Second Sunday in March. Advance local time only one hour ahead. | Energy Policy Act of 2005
SECCHI G&C | 24th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 71 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 68 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
SECCHI G&C | 25th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 78 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD perihelion on DOY 076 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 55th Momentum Dump - AHEAD only | 89 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
MOC | Begin Turbo Encoding for Space Weather | 90 | 90 | NA | NA | NA | Awaiting turbo decoding implementation at NOAA stations. Use macro 203. Advise SCF staff on dates for APL 18m testing. | Planning telecon, 4/29/08
S/C | 50th Momentum Dump - BEHIND only | -- | 92 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 56th Momentum Dump - AHEAD only | 119 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
RF | Switch downlink rate to 120 kbps downlink rate – AHEAD only | 119 | -- | NA | 120 | 231 | Macro 218, Bi-phase L. Need by May 4, 2013, Assumes 34 m subnet. RF margin 2 dB, 90% weather, & 10 deg elevation. | RF Lead email, 9/6/11
0.1/1.18/2.2/0.07/0.6/2.7
S/C | 51st Momentum Dump - BEHIND only | -- | 123 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 57th Momentum Dump - AHEAD only | 154 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 52nd Momentum Dump - BEHIND only | -- | 155 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 26th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 162 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 162 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
SECCHI G&C | 25th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 169 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND perihelion on DOY 166 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 58th Momentum Dump - AHEAD only | 189 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 53rd Momentum Dump - BEHIND only | -- | 189 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
RF | HGA Checkout and Calibration #18 | 192 | 192 | 2 hr prep, 1 hr execute |  | 232 | Need HEMT receiver | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 30 |  | SPE angle = 19 deg (AHEAD). SPE angle = 20 deg (BEHIND).
[5 empty] | 3.2/1/1.8/2.2/0/9.4 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
S/C | 59th Momentum Dump - AHEAD only | 221 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 54th Momentum Dump - BEHIND only | -- | 226 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
PWR | 3rd Battery Discharge Cycle - AHEAD only | 249 | -- | 2 hrs | 120 | 231 | Annually at aphelion. SSR playback will occur throughout. Backup with RT command to restore VT level to 13. | PWR Lead Email 10/12/11
0.1/1.18/2.2/0.07/0.6/2.7
SECCHI G&C | 27th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 253 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD aphelion on DOY 249 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 55th Momentum Dump - BEHIND only | -- | 256 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 60th Momentum Dump - AHEAD only | 258 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 26th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 260 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 263 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
| End of Extended Mission #3 | 273 | 273 | NA | NA | NA | Ends at FY2013
S/C | 56th Momentum Dump - BEHIND only | -- | 291 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 61st Momentum Dump - AHEAD only | 293 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
| End LGA Downlink on 70 m DSN subnet – BEHIND | -- | 302 | NA | NA | NA | At 3 dB margin, the 70m downlink at 12 bps ends on Oct 29, 2013. However, at 0.5 dB margin with 90% weather and 20 degrees elevation, the 70m can support downlinking at 12 bps at maximum S/C range. At 50% weather and 30 degrees elevation, downlink margin is 1.5 dB. Need 34m & 70m array for unfavorable conditions or lower elevation. | RF Lead email, 7/19/10
MOC | Daylight Saving Time Ends | 307 | 307 | NA | NA | NA | First Sunday in November. Set local time only one hour back. | Energy Policy Act of 2005
S/C | 57th Momentum Dump - BEHIND only | -- | 320 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 62nd Momentum Dump - AHEAD only | 327 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 28th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 337 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 335 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
| 1st Mercury Sun Disk Transit – AHEAD | 346 | -- | 5 hr 12 min | NA | NA | Dec 12th, 2013, Start = 0158z, Stop = 0710z | SEG-12-057
SECCHI G&C | 27th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 351 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND aphelion on DOY 360 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 63rd Momentum Dump - AHEAD only | 353 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 58th Momentum Dump - BEHIND only | -- | 353 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
PWR | 3rd Battery Discharge Cycle - BEHIND only | -- | 360 | 2 hrs | 120 | 231 | Annually at aphelion. SSR playback will occur throughout. Backup with RT command to restore VT level to 13. | PWR Lead Email 10/12/11
0.1/1.18/2.2/0.07/0.6/2.7
***** | 2014
RF | HGA Checkout and Calibration #19 | 9 | 9 | 2 hr prep, 1 hr execute |  | 232 | Need HEMT receiver | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 30 |  | SPE angle = 14 deg (AHEAD). SPE angle = 12 deg (BEHIND).
[5 empty] | 3.2/1/1.8/2.2/0/9.4 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
S/C | 64th Momentum Dump - AHEAD only | 20 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 59th Momentum Dump - BEHIND only | -- | 23 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
| End LGA Downlink on 70 m DSN subnet – AHEAD | 30 | -- | NA | NA | NA | At 3 dB margin, the 70m downlink at 12 bps ends on Jan 30, 2014. However, at 0.5 dB margin with 90% weather and 20 degrees elevation, the 70m can support downlinking at 12 bps at maximum S/C range. At 50% weather and 30 degrees elevation, downlink margin is 1.5 dB. Need 34m & 70m array for unfavorable conditions or lower elevation. | RF Lead email, 7/19/10
| End LGA Uplink on 70 m DSN subnet – BEHIND | -- | 39 | NA | NA | NA | At 6 dB margin, the 70m uplink at 7.8 bps ends on Feb 8, 2014. However, at 3 dB margin with 90% weather and 20 degrees elevation, the 70m can support uplinking at 7.8 bps at maximum S/C range. Need to increase transmit power to 20 kW. | RF Lead email, 7/19/10
S/C | 65th Momentum Dump - AHEAD only | 50 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 29th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 56 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD perihelion on DOY 055 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 60th Momentum Dump - BEHIND only | -- | 59 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
MOC | Daylight Saving Time Begins | 68 | 68 | NA | NA | NA | Second Sunday in March. Advance local time only one hour ahead. | Energy Policy Act of 2005
S/C | 66th Momentum Dump - AHEAD only | 87 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 28th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 91 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 92 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 61st Momentum Dump - BEHIND only | -- | 95 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
| 1st Mercury Sun Disk Transit – BEHIND | -- | 119 | 4 hr 19 min | NA | NA | April 29, 2014, Start = 0149z, Stop = 0608z | SEG-12-057
S/C | 67th Momentum Dump - AHEAD only | 122 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 62nd Momentum Dump - BEHIND only | -- | 127 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 30th SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 140 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 141 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
S/C | 68th Momentum Dump - AHEAD only | 156 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 63rd Momentum Dump - BEHIND only | -- | 160 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
| End LGA Uplink on 70 m DSN subnet – AHEAD | 172 | -- | NA | NA | NA | At 6 dB margin, the 70m uplink at 7.8 bps ends on June 21, 2014. However, at 3 dB margin with 90% weather and 20 degrees elevation, the 70m can support uplinking at 7.8 bps at maximum S/C range. Need to increase transmit power to 20 kW. | RF Lead email, 7/19/10
S/C | 69th Momentum Dump - AHEAD only | 187 | -- | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 15 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
S/C | 64th Momentum Dump - BEHIND only | -- | 187 | 2 hrs | 96 | 234 | Thruster set A, on HGA. Every 42 days. Dump at ~ 12 Nms system momentum.
3.2/3.2/3.6/2.2/0.6/26.1
SECCHI G&C | 29th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 196 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND perihelion on DOY 190 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
RF | HGA Checkout and Calibration #20 | 191 | 191 | 2 hr prep, 1 hr execute |  | 232 | Need HEMT receiver | RF email, 3/4/04. DAO email 8/3/05.
Desire GT on
[5 empty] | 30 |  | SPE angle = 8 deg (AHEAD). SPE angle = 8 deg (BEHIND).
[5 empty] | 3.2/1/1.8/2.2/0/9.4 |  | Disable autonomy rule 25 (Monitor HGA health) before each test.
Script: hga_calibration.prc
PWR | 4th Battery Discharge Cycle - AHEAD only | 228 | -- | 2 hrs | 120 | 231 | Annually at aphelion. SSR playback will occur throughout. Backup with RT command to restore VT level to 13. | PWR Lead Email 10/12/11
0.1/1.18/2.2/0.07/0.6/2.7
SECCHI G&C | 31st SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 231 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD aphelion on DOY 228 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
| End of Extended Mission #3 | 273 | 273 | NA | NA | NA | Ends at FY2014
SECCHI G&C | 30th SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 287 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 287 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
MOC | Daylight Saving Time Ends | 306 | 306 | NA | NA | NA | First Sunday in November. Set local time only one hour back. | Energy Policy Act of 2005
SECCHI G&C | 32nd SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 315 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. Midpoint on DOY 314 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
***** | 2015
PWR | 4th Battery Discharge Cycle - BEHIND only | -- | 19 | 2 hrs | 120 | 231 | Annually at aphelion. SSR playback will occur throughout. Backup with RT command to restore VT level to 13. | PWR Lead Email 10/12/11
0.1/1.18/2.2/0.07/0.6/2.7
SECCHI G&C | 31st SECCHI Stepped Calibration Roll (UT event) – BEHIND only | -- | 20 | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. BEHIND aphelion on DOY 019 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
SECCHI G&C | 33rd SECCHI Stepped Calibration Roll (UT event) – AHEAD only | 34 | -- | 3 hrs | NA | NA | Schedule when system momentum is below 10 Nms. Timetagged event (UT). Set to end 45 minutes before BOT due to G&C blackbox limitations. Every aphelion, perihelion, and midpoints between aphelion and perihelion. AHEAD perihelion on DOY 035 | SECCHI M-O-R presentation 11/10/04. PLASTIC Ops WGM 4/21/04. SECCHI Ops Lead email 11/30/07.
All | Begin Solar Conjunction - BEHIND | -- | 14 | NA | NA | NA | No communication due to S/C within ± 2.27 deg of the Sun. To increase the signal, disable ranging, & use lower downlink rate. MESSENGER had TLM till 1.13 deg of the Sun in 2007. | Solar conjunction planning 12/30/13, constraints - DSN = 2 deg, Sun diameter = 0.54 deg, 4/6/08
All | Begin Solar Conjunction - AHEAD | 42 | -- | NA | NA | NA | No communication due to S/C within ± 2.27 deg of the Sun. To increase the signal, disable ranging, & use lower downlink rate. MESSENGER had TLM till 1.13 deg of the Sun in 2007. | Solar conjunction planning 12/30/13, constraints - DSN = 2 deg, Sun diameter = 0.54 deg, 4/6/09
All | End 1st Solar Conjunction - BEHIND | -- | 78 | NA | NA | NA | No communication due to S/C within ± 2.27 deg of the Sun. | Solar conjunction planning 12/30/13
All | End Solar Conjunction - AHEAD | 189 | -- | NA | NA | NA | No communication due to S/C within ± 2.27 deg of the Sun. | Solar conjunction planning 12/30/14
G&C | Refresh IMU EEPROM | 299 | 299 | 30 min | 30 | 232 | Every 3 years | IMU manufacturer spec.
3.2/1/1.8/2.2/0/9.4
***** | 2016
| Begin LGA Uplink on 70 m DSN subnet – BEHIND | -- | 63 | NA | NA | NA | At 6 dB margin, the 70m uplink at 7.8 bps begins on March 3, 2016. | RF Lead email, 7/19/10
| Begin LGA Uplink on 70 m DSN subnet – AHEAD | 97 | -- | NA | NA | NA | At 6 dB margin, the 70m uplink at 7.8 bps begins on April 6, 2016. | RF Lead email, 7/19/10
***** | 2017
RF | Switch downlink rate to 160 kbps downlink rate - AHEAD | 189 | -- | NA | 160 | 235 | Macro 212, Bi-phase L. Need by July 11, 2017, Assumes 34 m subnet. RF margin 2 dB, 90% weather, & 10 deg elevation | RF Lead email, 7/23/10
0.1/1.18/2.2/0.07/0.6/2.7
RF | Switch downlink rate to 160 kbps downlink rate- BEHIND | -- | 203 | NA | 160 | 235 | Macro 212, Bi-phase L. Need by July 22, 2017, Assumes 34 m subnet. RF margin 2 dB, 90% weather, & 10 deg elevation | RF Lead email, 7/23/10
0.1/1.18/2.2/0.07/0.6/2.7
| Resume LGA Uplink on 34 m DSN subnet – AHEAD | 270 | -- | NA | NA | NA | 6 dB margin, resumes Sep 27, 2017 | RF Lead email, 7/23/10
***** | 2018
| Resume LGA Uplink on 34 m DSN subnet – BEHIND | -- | 31 | NA | NA | NA | 6 dB margin, resumes Jan 31, 2018 | RF Lead email, 7/23/10
| 2nd Mercury Sun Disk Transit – AHEAD | 64 | -- | 3 hr 7 min | NA | NA | March 5, 2018, Start = 0203z, Stop = 0523z | SEG-12-057
| Resume LGA Downlink on 34 m DSN subnet – BEHIND | -- | 146 | NA | NA | NA | 3 dB margin, resumes May 26, 2018. | RF Lead email, 7/23/10
| Resume LGA Downlink on 34 m DSN subnet – AHEAD | 179 | -- | NA | NA | NA | 3 dB margin, resumes June 28, 2018. | RF Lead email, 7/23/10
***** | 2019
***** | 2020
***** | 2021
***** | 2022
***** | 2023
| 2nd Mercury Sun Disk Transit – BEHIND | -- | 119 | 7 hr 47 min | NA | NA | May 4, 2023, Start = 2019z, Stop = May 5th, 0406z | SEG-12-057
************ | To be scheduled: ****************************************************************************************************************

## Offsets
Days from launch (launch day = day 1)
A1 | 303
P1 | 310
A2 | 315
P2 | 321
A3 | 326
P3 | 333
A4 | 340
P4 | 346
S1 | 349
S1+ | 355
A5 | 8
S2 | 21

## Change Record
Date | Change
2006-07-27 | Added event: Update of PBDFD in C&DH EE to day 5
Changed space weather to use convolutional rate r=1/6, macro 205 (NOAA email, 7/27/06)
2006-08-01 | Updated for August 31st launch day
2006-08-02 | Removed the following events since incorporated into HGA deployment script:
Event #12 - Change to RTDFD 232 - 30 kbps - Delta V maneuvers, S/C & Instruments, 3.2/1/1.8/2.2/0/84.
Event #14 (same as event #5) - Change to first week TLM generation/record/RT downlink for S/C HSKP
Deleted the following event since it is not needed (MOps macros always set desired TLM schedule):
Change APID Rate Table to normal 3 kbps generation in C&DH and EA EEPROM
Change G&C TLM Schedule to normal G&C and EA EEPROM
2006-08-07 | Added missing script names
2006-08-08 | Added RTDFD events before and after all delta V maneuvers and SECCHI 93 kbps RT TLM events.
2006-08-14 | Adjusted the order of the Day 3 events to account for the time of the Engineering Burn 1
Adjusted the order of the Day 4 events to put S/C events first.
Day 1, corrected Event #11 script name.
2006-08-24 | Moved Change SCLT delay to 24 hrs in C&DH and EA to 2nd track
Updated all SECCHI GT calibration events
Split MAG calibration roll and HGA slew into separate events
Added SWAVES Smooth Calibration Roll events (6)
Modified EUVI Flat Field Offpoint event to a UT event due to 4 hour duration
2006-08-28 | Updated IMPACT MAG roll event remarks.
2006-08-30 | Added test IMPACT MAG roll event post A3.
Changed 8 GT calibration events to UT events
Added disabling rule 25 to HGA end-to-end slew test.
2006-09-18 | Moved Load flight autonomy rules and macros event to second track due to short first track duration
Updated for Oct. 25th launch day
2006-09-29 | Updated for Oct. 26th (UTC) launch day
Added A1 Backup #2 maneuver event
2006-10-04 | Set EB2 to 1 day after IMPACT boom deployment
2006-10-05 | Changed HGA end to end slew test for IMPACT to one 0 to 180 deg for 1st and 180 to 0 deg for 2nd test.
Deleted SECCHI Crack Doors Open on day 6 - ref. SECCHI Ops Lead email 10/4/06
Added abort and enable SECCHI decontamination heater duty cycle events to day 28 - ref. SECCHI Ops Lead email 10/4/06
Added GT enable/disable script name
2006-10-10 | Added Switch G&C to use PDU side A/B events for Engineering Burn #2
2006-10-12 | Removed Event #11 - Uplink Resweep, since it will decrease the amount of NAV data
2006-10-16 | Added clearing rules 189 & 190 fire counts to Change SCLT delay to 24 hrs in C&DH and EA
Added Disable Rule 25 event to day 1
Added Enable Rule 25 event to day 53 (STA) and day 83 (STB)
Added Increase Visible Couter Packets Frequency event to day 1
Added Clear Autonomy Counters event to day 1
Added Start SSR Playback event post maneuver
2006-10-17 | Added SECCHI event changes from SECCHI Ops Lead email on 10/13/06
Added HGA Stepped Slew Test on day 9
2006-10-27 | Changed day offsets to DOY based on launch day of 10/26/06
Removed instrument power down and up for A1P maneuver
2006-11-03 | Corrected macro 213 to 237 for all post SECCHI events.
2006-11-20 | Hid dates in the past
Added Switch G&C TLM Schedule event to GT Enable on DOY 333
Added Saturday, Sunday, and Week # notations
A4P maneuver now on DOY 340 and A4B on DOY 341
2006-11-21 | Deleted A4 maneuver on AHEAD
Added HGA Auto Track test on DOY 333
2006-11-29 | Deleted instrument power off/on for P4, S1+, and A5
Deleted 3rd RT SECCHI GT Cal.
Moved events that require coordination between S/C and instrument off of weekends.
Added IMPACT MAG smooth rolls in RT at P4
2006-11-30 | Moved HI cover opening on AHEAD
Moved 2nd & 3rd SECCHI GT calibrations to DOY 352 & 354
2006-12-04 | Changed A5P date to Jan 8th
Changed A5B date to Jan 11th
Changed 2nd SECCHI GT calibrations to DOY 350 for BEHIND
2006-12-19 | Added downlink rate events on LGA
Added to be scheduled events
2006-12-29 | Moved 3rd HGA calibrations
Added downlink rate switches for all rates
Added all TLM Planning events
2007-01-10 | Adjusted HGA calibration events for latest implementation plan
Changed 3rd SWAVES Cal. Roll to DOY 031
Begin using SPS on DOY 016
2007-01-15 | Adjusted lunar transit times for BEHIND on DOY 056
2007-02-08 | Updated 1st SECCHI Campaign dates
Added switch to CCSDS SLE TLM service in Jan 09
Added daylight savings time begin/end events
Added IMU EEPROM refresh event
2007-03-20 | Added SECCHI Stepped Roll and SECCHI GT Offpoint on DOY 107 & 109 respectively
2007-03-23 | Adjusted C&DH macro 0 changes to be on the same DOY if appropriate.
2007-03-27 | Added minimum mission success note.
2007-04-02 | Adjusted EEPROM update events to occur on a Wednesday
2007-04-16 | Added HGA calibration events every 3 months through the EOPM
Added Start unattended track ops
2007-05-14 | Added disable HGARA at 89.9 deg event for AHEAD only
2007-05-22 | Added test macro 145 event on DOY 178, STA only
2007-06-13 | Added 4th & 5th, and 6th, 7th, & 8th momentum dump events, DOY 206 & 269 and 186, 227, & 269 respectively
2007-08-27 | Added AHEAD 9th, 10th, & 11th, and BEHIND 6th & 7th momentum dump events, DOY 311, 353, 030 and 332 & 030 respectively.
2007-09-12 | Added 2nd SECCHI Campaign on 2008:007 thru 020 and deleted disable HGARA at 89.9 deg event for AHEAD only
2007-10-15 | Added EOPM and start of extended mission #1
2007-12-03 | Removed Jan 08 and Oct 08 HGA calibrations
Added final macro 0 change for using emergency data rates on LGA (macro 200)
Added HGA calibration events every 3 months through the EOEM #1 (Feb 2011)
Added SECCHI Stepped Cals every aphelion and perhelion and midpoints in between from Jan 2008 through EOPM.
7th BEHIND momentum dump changed to DOY 023
Added momentum dumps through the EOPM
2007-12-10 | Adjusted AHEAD momentum dump event dates by one week
2008-01-17 | Adjusted AHEAD & BEHIND momentum dump event dates to account for aphelion and perhelion effects.
Added 2nd PPT events to both S/C
2008-04-18 | Added and adjusted downlink rate changes from 480 to 30 kbps for 34 m and 70 m DSN subnets (70m in green)
Added end of LGA uplink and downlink events for 34 m and 70 m DSN subnets
Added solar conjunction dates (yellow background)
Adjusted dates for all macro 0 LGA data rates events using latest RF link analysis.
Deleted 2nd PPT events on both S/C
Added SECCHI Stepped Cals every aphelion and perhelion and midpoints in between from EOPM through 2010.
2008-04-29 | Added turbo encoding use for space weather event on Oct 2009 for both S/C.
2008-05-20 | Added switch to 6 hour track durations on 2009:215.
Added L4 & L5 libration point events at 2009:255 & 2009:299 respectively.
Added momentum dumps through 2009
2008-07-08 | Added low system momentum scheduling constraint for SECCHI Stepped Cal. events.
2008-07-10 | Added dates for 34 m use of 240 and 120 kbps downlink rates.
2008-07-28 | Adjusted switch to 480 kbps event dates for 1.5 dB vice 3 dB RF link margin.
2009-01-13 | Added 6, 7, and 8 hour track durations.
Added HGA calibrations for 2011 through 2012
Adjusted HGA calibrations to every 6 months
Added G&C 3.2.6 and Autonomy release loading, and System Reset events as to be scheduled.
2009-02-09 | Moved SECCHI stepped cal. From DOY 069 to 097
Adjusted BEHIND momentum dump frequency to every 42 days @ 12 Nms system momentum
2009-03-10 | Adjusted switch to 360, 240, & 160 kbps downlink rate dates.
Adjusted switch to 6, 7, & 8 hour DSN track dates.
Added SECCHI 180 degree roll events every 4 weeks until reaching L4 & L5
Added system reset for G&C 3.2.6 version on BEHIND - needs GSFC approval
Added IMU2 checkout for BEHIND
2009-07-06 | Added system reset for G&C 3.2.6 version on AHEAD
2009-08-24 | Removed SECCHI HI 180 roll events after DOY 225 - SECCHI team discontinued
Added loading G&C 3.2.6 FSW to copy 1 EEPROM
2009-09-15 | Readded deleted BEHIND 11th SECCHI Stepped Cal. Event on 2009-265
Adjusted BEHIND momentum dump dates
2009-09-24 | Moved space weather to turbo encoding event to 1/1/10
Moved loading G&C FSW 3.2.6 to EEPROM copy 1 to 1/1/10
2009-10-01 | Changed SECCHI Stepped Cal events to end 45 minutes before BOT due to OWLT.
2009-10-22 | Added Refresh IMU EEPROM to 2012 and 2015
Added Refresh ST EEPROM to 2011 and 2016
2010-03-18 | Added Load G&C 3.2.6 FSW to Copy 1 EEPROM
2010-03-23 | Adjusted LGA use end dates
2010-07-22 | Added SECCHI Stepped Cal events through 2014
Added HGA Cal events through 2014
Added momentum dumps through 2011
Updated data rate usage through 2015
2010-09-03 | Adjusted 70m data rates based on RF analysis of 7/23/10
2012-12-27 | Added Battery Discharge Cycle events through 2014
Added EOEM #3
2014-01-08 | Remove BEHIND use of 360 kbps downlink rate on 70m as not needed.